## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Sherpur Village zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000060/2022-2023 | 175/A/DSD | 18/04/2022 | 18/05/2022 | BALAJEE ENTERPRISE | 1.54 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- I , Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000816/2021-2022 | 48/DSD | 07/02/2022 | 22/02/2022 | BALAJEE ENTERPRISE | 4.95 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-VI within Kaliganj Block(Phase-C) | Assistant Engineer | Junior Engineer 3 | ORD/000356/2021-2022 | 7058/ND | 06/12/2021 | 06/03/2022 | BALAJEE ENTERPRISE | 176.9 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 429/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 4309/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.88 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VI within Kaliganj Block. (Phase-C) | SM/08961 | Retrofitting | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000003/2024-2025 | 918KlySD-I | 07/06/2024 | 22/06/2024 | UMWELT ENGINEER PVT LTD | 13.46 | 0 | 0 | 100
Total | [13 empty] | 223.72 | 0 | 0