## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Bara Andulia(Zone-I) W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000278/2021-2022 | 5690/ND | 03/11/2021 | 01/02/2022 | H I ENTERPRISE | 98.23 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2021-2022 | 144/ Kly SD-II | 31/01/2022 | 31/01/2023 | SUMAN CHAKRABORTY | 4.8 | 0 | 0 | 65
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Kalyani Sub-Division-I, PHE Dte. | Assistant Engineer |  | ORD/000750/2021-2022 | 287/Kly SD-I | 31/03/2022 | 31/03/2023 | SATYABRATA CHAKRABORTY | 4.8 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 441/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000078/2021-2022 | 782/ND | 18/02/2022 | 18/02/2022 | Resource Division | 4.39 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000104/2021-2022 | 1022/ND | 03/03/2022 | 03/03/2022 | Resource Division | 7.9 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000316/2025-2026 | 4504/ND | 18/09/2025 | 17/12/2025 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Baraandulia Zone-I Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08963 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 287.19 | 0 | 0