## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Krishnaganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000281/2021-2022 | 5693/ND | 03/11/2021 | 01/02/2022 | NILAY KUMAR BHATTACHARYA | 85.63 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.01.2024 to 31.01.2024 |  |  | ORD/000827/2023-2024 | 1359/KLYSD-I | 28/12/2023 | 28/01/2024 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Providing balance FHTC of Phase I (Retrofitting) of Krishnaganj Water Supply Scheme in Nadia District Under Krishnagar Sub-Division, of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000296/2022-2023 | 5335/ND | 21/12/2022 | 21/03/2023 | NILAY KUMAR BHATTACHARYA | 96.45 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.02.2024 to 31.03.2024 | Assistant Engineer | Junior Engineer 2 | ORD/000864/2023-2024 | 115/KlySD-I | 31/01/2024 | 29/02/2024 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.03.2024 to 31.03.2024 | Assistant Engineer | Junior Engineer 2 | ORD/000946/2023-2024 | 326/KlySD-I | 29/02/2024 | 31/03/2024 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Krishnaganj Water Supply Scheme under Jal Swapna Program in Nadia District under Nadia Division, P.H.E Dte. (Phase-I, Retrofitting) | SM/08964 | Retrofitting | Laying Of Additional Distribution System Including Specials, Valves to provide FHTC at Leftout Household, Inter Connection of Rising Main in connection to Retrofitting (Phase-I) under JJM In Ground Based Piped Water Supply Scheme at Krishnaganj Majhdia to accommodate FHTC within Krishnaganj Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000772/2023-2024 | 1762/ND | 12/03/2024 | 12/08/2025 | NILAY KUMAR BHATTACHARYA | 30.36 | 0 | 0 | 100
Total | [13 empty] | 227.1 | 0 | 0