## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000004/2022-2023 | 339/Kly SD-I | 18/04/2022 | 21/04/2022 | RAJAT ENTERPRISE | 1.69 | 1.7 | 100.49 | 0
2 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. |  |  | VCH/000505/2022-2023 | 72/PFMS | 05/07/2022 | 05/07/2022 | OTHERS | 13.8 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000422/2022-2023 | 218/Kly SD-I | 22/02/2023 | 23/05/2023 | CONSTRUCTURE | 0.95 | 0.95 | 100 | 0
4 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | Continuation for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000022/2023-2024 | 578/ Kly SD-I | 02/05/2023 | 31/07/2023 | CONSTRUCTURE | 0.95 | 0.95 | 100 | 0
5 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | Continuation work order for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. for the period from 01.08.2023 to 31.10.2023 | Assistant Engineer |  | ORD/000177/2023-2024 | 791/KLYSD-I | 27/07/2023 | 27/10/2023 | CONSTRUCTURE | 0.95 | 0.9 | 94.49 | 100
6 | NADIA |  | Nadia Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. | SM/09024 | Support-WQMSP | PLACEMENT OF FUND FOR ASHA INCENTIVE OF WATER SAMPLE TESTING BY FTK AT DIFFERENT BLOCKS IN THE DISTRICT OF NADIA |  |  | BILL/00668/2022-2023 | 492/PFMS | 27/03/2023 | 27/03/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 7.7 | 0 | 0 | 0
Total | [13 empty] | 26.05 | 4.5 | 17.29