## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 7048/ND | 06/12/2021 | 06/12/2021 | Resource Division | 35.82 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2021-2022 | 785/ND | 18/02/2022 | 18/02/2022 | Resource Division | 16.47 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 0 | 0 | 60
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 26/10/2024 | IMAGIN | 34.21 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Karimpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte."(Phase-1 Retro fitting) " | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000602/2021-2022 | 350/ND | 25/01/2022 | 09/01/2025 | TARUN KUMAR BHATTACHARYA | 404.96 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 206 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000081/2024-2025 | 4166/ND | 30/07/2024 | 25/07/2025 | HARBAUER INDIA (P) LTD. | 444.71 | 0 | 0 | 30
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Karimpur W/S to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000793/2024-2025 | 7465/ND | 20/12/2024 | 20/03/2025 | CHOWDHURY & CO. | 128.29 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karimpur to Accommodate FHTC | SM/09033 | Augmentation | Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. | Assistant Engineer |  | ORD/000759/2021-2022 | 289/Kly SD-I | 31/03/2022 | 29/06/2022 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
Total | [13 empty] | 1103.57 | 0 | 0