## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer |  | ORD/000254/2023-2024 | 901/KlySD-I | 25/08/2023 | 25/11/2023 | GOUTAM DAM | 0.5 | 0.17 | 33.33 | 100
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF:01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer |  | ORD/000252/2023-2024 | 900/KLYSD-I | 25/08/2023 | 25/11/2023 | JOYDEV JANA | 0.5 | 0.17 | 33.33 | 100
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer |  | ORD/000253/2023-2024 | 902/KLYSD-I | 28/08/2023 | 28/11/2023 | SUCHITRA GHOSH | 0.23 | 0.08 | 33.33 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | laying of distribution pipe line180mm dia UPVC pipe etc. for Providing functional household tap connection at Naserkuli zone- I W/S scheme under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Ranaghat - II Block | ORD/000721/2021-2022 | 1464/PH | 03/03/2022 | 13/03/2022 | SAIKAT GHOSH | 1.26 | 1.26 | 100 | 100
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/01/2023 to 31/03/2023 (Three months). | Assistant Engineer |  | ORD/000310/2022-2023 | 1231/Kly SD-I | 30/12/2022 | 30/03/2023 | M/S S.K. ENTERPRISE | 0.8 | 0.27 | 33.33 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000062/2023-2024 | 658/KLYSD-I | 24/05/2023 | 24/08/2023 | SUCHITRA GHOSH | 0.23 | 0.08 | 33.33 | 70
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000060/2023-2024 | 656/KLYSD-I | 24/05/2023 | 24/08/2023 | JOYDEV JANA | 0.5 | 0.17 | 33.33 | 70
8 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/07/2023 to 30/09/2023 (Three months). |  | Junior Engineer 2 | ORD/000063/2023-2024 | 710/KlySD-I | 19/06/2023 | 19/09/2023 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100 | 100
9 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000061/2023-2024 | 657/KlySD-I | 24/05/2023 | 24/08/2023 | GOUTAM DAM | 0.5 | 0.17 | 33.33 | 70
10 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000069/2021-2022 | 802/ND | 18/02/2022 | 18/02/2022 | Resource Division | 2.2 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | PAYMENT FOR NGO LAB |  |  | BILL/00731/2023-2024 | 281/PFMS | 19/09/2023 | 19/09/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.4 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | PAYMENT FOR NGO LAB. |  |  | BILL/00730/2023-2024 | 280/PFMS | 19/09/2023 | 19/09/2023 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 5.42 | 5.65 | 81
14 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kamalpur ZoneII Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/09042 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Kamalpur Z-II Water Supply scheme Ranaghat-II block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000246/2021-2022 | 5701/ND | 03/11/2021 | 30/11/2024 | PRIYA CONSTRUCTION | 63.6 | 49.83 | 78.35 | 100
Total | [13 empty] | 167.91 | 58.39 | 34.78