## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/09044 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000113/2021-2022 | 1024/ND | 03/03/2022 | 03/03/2022 | Resource Division | 0.7 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/09044 | Retrofitting | URGENT RESTORATION OF CARRIAGE WAY & FLANF OF BADKULLA- ARANGHATA ROAD AT CH. 5.7 KM. " ARISING DUE TO LAYING OF PHED W/S SCHEME PIPE LINE, HIGHWAY DIVISION -II, PW ROADS. |  |  | BILL/00528/2023-2024 | 242/1/PFMS | 18/08/2023 | 18/08/2023 | OTHERS | 0.98 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/09044 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from MuktadahaZone-II Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/09044 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Muktadaha Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte | Assistant Engineer |  | ORD/000276/2021-2022 | 5688/ND | 03/11/2021 | 02/01/2022 | CHOWDHURY & CO. | 39.38 | 0 | 0 | 100
Total | [13 empty] | 137.07 | 0 | 0