## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/09046 | Retrofitting | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. |  |  | VCH/001117/2021-2022 | 696/PFMS | 28/03/2022 | 28/03/2022 | MALI CONSTRUCTION | 38.98 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/09046 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H.E. Dte., Kalyani, Nadia. Period of work 01-03-2022 to 28-02-2023 | Assistant Engineer |  | ORD/000814/2021-2022 | 118/RSD | 28/02/2022 | 05/11/2022 | SUMAN CHAKRABORTY | 3.85 | 1.8 | 46.67 | 75
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/09046 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 440/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.19 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/09046 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000074/2021-2022 | 820/ND | 18/02/2022 | 18/02/2022 | Resource Division | 3.44 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Teinpur Zone-IIWater Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/09046 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Teinpur Zone-II W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000275/2021-2022 | 5687/ND | 03/11/2021 | 01/02/2022 | MALI CONSTRUCTION | 67.51 | 7.32 | 10.84 | 100
Total | [13 empty] | 114.98 | 9.11 | 7.93