## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II |  |  | VCH/001060/2021-2022 | 618/PFMS | 14/03/2022 | 14/03/2022 | UMWELT ENGINEERS PVT LTD | 2.84 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 94/ND | 06/01/2022 | 06/01/2022 | Resource Division | 0.66 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000084/2021-2022 | 819/ND | 18/02/2022 | 18/02/2022 | Resource Division | 6.28 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000131/2021-2022 | 1260/ND | 16/03/2022 | 16/03/2022 | Resource Division | 0.66 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by Augmentation under Jal Swapna for Ghoralia Zone-II Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Santipur Block | ORD/000599/2021-2022 | 337/ND | 25/01/2022 | 25/04/2022 | S.S. ENTERPRISE | 108.63 | 88.37 | 81.35 | 98
6 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 27/01/2025 | IMAGIN | 34.21 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Ghoralia Zone II | SM/09089 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir capacity of 136 CUM, existing Pump Houses and construction of shed for CWR at Existing Headwork site along with other allied Works at Ghoralia Zone II water supply scheme under Tehatta Subdivision of Nadia Division. | Assistant Engineer | Junior Engineer Santipur Block | ORD/000791/2024-2025 | 763/ND | 19/02/2025 | 18/08/2025 | M/S ARATI ENTERPRISE | 27.7 | 0 | 0 | 60
Total | [13 empty] | 180.96 | 88.37 | 48.83