## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I |  |  | VCH/001059/2021-2022 | 617/PFMS | 14/03/2022 | 14/03/2022 | UMWELT ENGINEERS PVT LTD | 3.94 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Providing (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Paschim Bhatjangla Zone -I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000601/2021-2022 | 336/ND | 25/01/2022 | 25/04/2022 | PUSPA ENTERPRISE | 314.25 | 267.8 | 85.22 | 95
3 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000016/2021-2022 | 2152/ND | 21/05/2021 | 20/07/2021 | ORIENT CONSTRUCTION | 42.68 | 12.75 | 29.87 | 100
4 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | laying of distribution pipe line75mm dia and 63 mm dia UPVC pipe etc. for Providing functional household tap connection at Paschim Bhatjangla zone- I W/S scheme (Part - A) under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000240/2021-2022 | 1070/PH | 04/10/2021 | 19/10/2021 | ORIENT CONSTRUCTION | 4.79 | 4.79 | 100 | 100
5 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000707/2023-2024 | 1251/ND | 22/02/2024 | 20/08/2024 | APURBA MANDAL | 163.44 | 0 | 0 | 45
6 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000073/2024-2025 | 4073/ND | 26/07/2024 | 12/04/2026 | SANDIP BISWAS | 148.49 | 0 | 0 | 70
7 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000670/2023-2024 | 543/ND | 24/01/2024 | 26/09/2025 | G.S. CONSTRUCTION & CO | 39.9 | 0 | 0 | 60
8 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme for Paschim Bhatjangla Zone I | SM/09090 | Retrofitting | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000187/2024-2025 | 5035/ND | 13/09/2024 | 28/10/2024 | ZEST INFRACON | 16.29 | 0 | 0 | 60
Total | [13 empty] | 733.79 | 285.34 | 38.89