## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH | SM/09093 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub- Divn under Nadia Divn, PHE Dte |  |  | VCH/001124/2021-2022 | 710/PFMS | 30/03/2022 | 30/03/2022 | OTHERS | 17.48 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH | SM/09093 | Retrofitting | Providing FHTC (Functional Household Tap Connection) by retrofitting under "Jalswapno" in connection with " Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Bankar Dhopadi W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer |  | ORD/000411/2021-2022 | 7294/ND | 20/12/2021 | 18/02/2022 | SK RAJU | 32.6 | 5.33 | 16.36 | 0
3 | NADIA |  | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH | SM/09093 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 7451/ND | 27/12/2021 | 27/12/2021 | Resource Division | 11.31 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH | SM/09093 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 4325/ND | 29/09/2022 | 29/09/2022 | Resource Division | 1.26 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno with shifting of existing PHE Pipeline for implementation of widening and strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Kmp under NH | SM/09093 | Retrofitting | Additional FHTC by retrofitting unfer jalswapno in connection with shifting of existing pipeline for implementation of widening and strengthening work of Swarupganj UBI more to Anandabas Road from 0.00 km to 6.10 km under NH Divn-I RIDF-XXV within Bankar Dhopadi Water supply scheme under Krishnagar Sub-Division PHED. (Sl.No. 01) | Assistant Engineer | Junior Engineer 2 | ORD/000053/2022-2023 | 573/KSD | 13/06/2022 | 12/08/2022 | SUBHASIS MAJUMDER | 4.57 | 4.34 | 95.01 | 97
Total | [13 empty] | 67.21 | 9.67 | 14.39