## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. |  |  | VCH/001066/2021-2022 | 629/PFMS | 16/03/2022 | 16/03/2022 | UMWELT ENGINEERS PVT LTD | 3.23 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000600/2021-2022 | 338/ND | 25/01/2022 | 25/04/2022 | JOY HIND TUBEWELL'S | 156.61 | 0 | 0 | 80
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Supply delivery & installation of submersible P/m alongwith allaied electrical mechanical works voltage stabilizer and automatic chlorinator etc. rejuvenation to Accomodate FHTC at P.h no.I & II under Bablari Dewanganj w/s scheme Block--Nabawdip Dist- Nadia |  |  | ORD/002729/2022-2023 | 6183/EMD | 14/11/2022 | 14/12/2022 | M.S. ENTERPRISE | 15.63 | 0 | 0 | 75
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 4293/ND | 29/09/2022 | 29/09/2022 | Resource Division | 4.16 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000016/2023-2024 | 1847/ND | 26/04/2023 | 25/06/2023 | A.K.ADHIKARY | 15.77 | 0 | 0 | 95
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 250 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000396/2023-2024 | 5125/ND | 17/11/2023 | 15/02/2024 | SANJIB DEY | 24.91 | 0 | 0 | 98
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Providig FHTC at leftout household in connection to the Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000721/2023-2024 | 1372/ND | 28/02/2024 | 08/01/2025 | A.K.ADHIKARY | 21.74 | 0 | 0 | 70
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Conversion of IEP to AIRP of capacity 46 Cu.m/hr at Bablari Dewanganj Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000794/2023-2024 | 1906/ND | 15/03/2024 | 24/01/2026 | DEBASIS SAMADDAR | 104.21 | 0 | 0 | 70
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bablari Dewanganj Water Supply Scheme. | SM/09205 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 443.22 | 0 | 0