## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. |  |  | VCH/001143/2021-2022 | 706/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.63 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. |  |  | VCH/001130/2021-2022 | 713/PFMS | 30/03/2022 | 30/03/2022 | SUMAN CHAKRABORTY | 27.16 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Laying of Distribution system for providing FHTC at Dafarpota (Zone-II) Water Supply Scheme in Nadia District under Krishnagar Sub-Division ,P.H.E.Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000297/2022-2023 | 5336/ND | 21/12/2022 | 20/01/2023 | PURNIMA ELECTRICS & DECORATORS | 12.79 | 7.61 | 59.49 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 98/ND | 06/01/2022 | 06/01/2022 | Resource Division | 5.53 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 4284/ND | 29/09/2022 | 29/09/2022 | Resource Division | 2.66 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dafarpota Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000506/2023-2024 | 6083/ND | 19/12/2023 | 18/03/2024 | M/S CHANDIMATA CONSTRUCTION | 21.51 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Dafarpota Zone-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000495/2021-2022 | 66/ND | 05/01/2022 | 21/03/2022 | SUMAN CHAKRABORTY | 52.5 | 19.99 | 38.09 | 90
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.10.2023 to 30.11.2023 | Assistant Engineer | Junior Engineer 2 | ORD/000414/2023-2024 | 1034/KLYSD-I | 29/09/2023 | 29/10/2023 | SUMAN CHAKRABORTY | 4.89 | 0.19 | 3.96 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | Assistant Engineer | Junior Engineer 2 | ORD/000456/2023-2024 | 1260/KLYSD-I | 30/11/2023 | 31/12/2023 | SUMAN CHAKRABORTY | 4.89 | 0.06 | 1.3 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Emergent Repairing work in connection with Augmentation of Ground Based piped water supply scheme at Bablari Dewanganj W/S scheme within Nabadwip block under Krishnaganj Sub-Division under Nadia Division. | Assistant Engineer |  | ORD/000533/2022-2023 | 220/KSD | 03/03/2023 | 18/03/2023 | SAMAR ENTERPRISE | 0.3 | 0.24 | 79.3 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 0.34 | 1 | 60
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Conversion of IEP to AIRP of capacity 10 Cu.m/hr at Daforpota Zone-II Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000793/2023-2024 | 1905/ND | 15/03/2024 | 06/09/2025 | SANDIP BISWAS | 63.46 | 0 | 0 | 70
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dafarpota-II water supply Scheme. | SM/09206 | Augmentation | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2024 to 31-07-2024= 182 days. | Assistant Engineer | Junior Engineer 2 | ORD/000718/2023-2024 | 125/RSD | 29/01/2024 | 29/07/2024 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.18 | 0 | 0 | 50
Total | [13 empty] | 235.71 | 28.44 | 12.07