## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Chapra Bangaljhi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000280/2021-2022 | 5692/ND | 03/11/2021 | 01/02/2022 | M/S GHOSH CONSTRUCTION | 86.03 | 83.18 | 96.69 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 426/ND | 31/01/2022 | 31/01/2022 | Resource Division | 3.58 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000787/2023-2024 | 1898/ND | 15/03/2024 | 11/09/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 27/01/2025 | IMAGIN | 34.21 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 606.32 | 83.18 | 13.72