## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Chapra Bangaljhi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(PART-A) | Assistant Engineer |  | ORD/000280/2021-2022 | 5692/ND | 03/11/2021 | 01/02/2022 | M/S GHOSH CONSTRUCTION | 86.03 | 83.18 | 96.69 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 426/ND | 31/01/2022 | 31/01/2022 | Resource Division | 3.58 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 27/01/2025 | IMAGIN | 34.21 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 174 m3/hr at Chapra Bangaljhi Water Supply Scheme within Chapra Block under Krishnagar Sub- Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000787/2023-2024 | 1898/ND | 15/03/2024 | 11/09/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 385.52 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000721/2024-2025 | 7570/ND | 27/12/2024 | 10/02/2025 | IMAGIN | 19.44 | 6.31 | 32.48 | 100
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Additional Work in connection to Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Chapra Bangaljhi Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4,Junior Engineer 5 | ORD/000013/2025-2026 | 1777/ND | 21/04/2025 | 20/06/2025 | S.B.CONSTRUCTION | 9.42 | 0 | 0 | 70
8 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from ChapraBangaljhi Water Supply Scheme under Jal Swapna Program inNadia District under Nadia Division, P.H.E Dte. (Phase-I,Retrofitting) | SM/09222 | Retrofitting | Advance payment for road restoration of work "Krishnagar majdia Road from 24.26 Km to 24.66 Km for damaged restoration work against the work of 'laying of pipeline under JJM Scheme PHE Dte' under Nadia Highway Division No-I in the district of Nadia during the year 2024-25." |  |  | BILL/00924/2024-2025 | BP-2024-025-375 | 18/03/2025 | 18/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 9.73 | 0 | 0 | 0
Total | [13 empty] | 644.91 | 89.5 | 13.88