## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nabadwip | Central Drilling | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000172/2020-2021 | 86/ CMSD-II (D) | 24/02/2021 | 26/03/2021 | ASHUTOSH DAS & CO | 4.83 | 0 | 0 | 0
2 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer |  | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 17/12/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
3 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Gadigacha W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 14) | Assistant Engineer | Junior Engineer 4 | ORD/000353/2021-2022 | 917/KSD | 29/11/2021 | 14/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.23 | 0 | 0 | 0
4 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Material Requisition To Resource Division |  |  | RTOR000171/2022-2023 | 132/ND | 06/01/2023 | 06/01/2023 | Resource Division | 29.03 | 0 | 0 | 0
5 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 3 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 28/12/2024 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
6 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Gadigacha Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000780/2023-2024 | 1894/ND | 15/03/2024 | 11/09/2024 | G.D. CONSTRUCTION AND CO. | 226.16 | 0 | 0 | 0
7 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 270/ND | 11/01/2024 | 11/01/2024 | Resource Division | 23.16 | 0 | 0 | 0
8 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Laying of Distribution System including specials & valves, pipe Supporting structure all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Soil investigation for construction of one No. 450 Cum OHR, Construction of R.C.C. Elevated Reservoir of 450 Cum capacity(including pile foundation) at Gadigachha in Nabadwip Block under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000088/2023-2024 | 3026/ND | 14/07/2023 | 14/07/2026 | JOY HIND TUBEWELL'S | 431.93 | 0 | 0 | 45
9 | NADIA | Nabadwip | Eastern Mechanical | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Gadigachha ground water based water supply scheme under Block_Nabadwip Dist. - Nadia under EMD, PHE Dte. SM/09223 | Assistant Engineer |  | ORD/000189/2025-2026 | 1127/EMD | 04/06/2025 | 02/09/2025 | ASHUTOSH DAS & CO. | 36.75 | 0 | 0 | 0
10 | NADIA | Nabadwip | Nadia Division | Gadigachha Piped Water Supply Scheme. | SM/09223 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 859.06 | 0 | 0