## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-II under Bayra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001913/2022-2023 | 6184 EMD | 14/08/2022 | 13/09/2022 | TALUKDER & CO. | 8.94 | 0 | 0 | 100
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at PH-I & II (Zone-II) under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | Assistant Engineer | Junior Engineer | ORD/002002/2022-2023 | 6184 / EMD | 14/08/2022 | 13/09/2022 | TALUKDER & CO. | 8.94 | 8.94 | 100 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Laying of Distribution System including specials & valves, pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting, fixing of 15mm NB PVC(schedule 80)/ 20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddale piece etc.by retrofitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000671/2021-2022 | 662/ND | 11/02/2022 | 12/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 458.3 | 313.34 | 68.37 | 78
4 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 4296/ND | 29/09/2022 | 29/09/2022 | Resource Division | 22.45 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte |  |  | VCH/001116/2021-2022 | 695/PFMS | 28/03/2022 | 28/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 38.35 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte |  |  | VCH/001053/2021-2022 | 611/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.18 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Badlangi Padmamala Zone - II PWSS in Pathuria & Dompukur Mouza within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000032/2024-2025 | 3432/ND | 19/06/2024 | 11/12/2025 | S.S.INFRASTRUCTURE | 73.72 | 0 | 0 | 80
8 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Conversion of IEP to AIRP of capacity 120 Cu.m/hr at Badlangi Padmamala Zone-II Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000801/2023-2024 | 1913/ND | 15/03/2024 | 01/09/2026 | MONDAL PRECISION PRIVATE LIMITED | 194.64 | 0 | 0 | 20
9 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Badlangi Padmamala Zone - II PWSS in Bania Khari & Chotta Andulia Mouza within Chapra Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000066/2024-2025 | 3899/ND | 16/07/2024 | 12/01/2025 | J.P. CONSTRUCTION & SUPPLIERS | 75.72 | 8.73 | 11.53 | 60
10 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000672/2024-2025 | 7451/ND | 20/12/2024 | 16/09/2025 | ROY ASSOCIATES | 85.97 | 0 | 0 | 25
11 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Srevice Road for Badlangi Padmamala Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000719/2023-2024 | 1303/ND | 23/02/2024 | 23/05/2024 | B.S. ENTERPRISE | 34.23 | 23.34 | 68.2 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-V), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000697/2023-2024 | 221/KLYSD-I | 09/02/2024 | 09/08/2024 | TECHVISION | 4.85 | 4.85 | 100 | 100
13 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 3.16 | 9.24 | 60
14 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VII), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000158/2024-2025 | 1220/KlySD-I | 09/08/2024 | 09/02/2025 | TECHVISION | 4.85 | 4.85 | 100 | 100
15 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 26/10/2024 | IMAGIN | 34.21 | 0 | 0 | 100
16 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VIII), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000159/2024-2025 | 1221/KlySD-I | 09/08/2024 | 09/02/2025 | TECHVISION | 4.85 | 4.85 | 100 | 100
17 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Reimbursement of Additional GST due to enhancement of rate from 12% to 18% vide notification no. 03/2022 central Tax Rate dt. 13.07.2022. of Laying of Distribution System including specials & valves,pipe supporting structure all complete and Providing FHTC including supplying,laying,fitting,fixing of 15mm NB PVC(schedule 80)/20mm OD HDPE(PE100,PN16) pipe with all necessary specials,10mm gun metal ferrule,saddle piece etc. by retroffitting under Jal Swapna for Badlangi Padmamala Zone-II Water Supply Scheme in Nadia District under Nadia Division PHE Dte. |  |  | BILL/00246/2024-2025 | 150/PFMS | 31/07/2024 | 31/07/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 6.5 | 0 | 0 | 0
18 | NADIA |  | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BADELANGI PADMAMALA ZONE-II ground water based water supply scheme under Block_ CHAPRA Dist. - Nadia under EMD, PHE Dte. SM/09450 | Assistant Engineer |  | ORD/000177/2025-2026 | 1113/EMD | 04/06/2025 | 02/09/2025 | BIDYUT KUMAR MUKHERJEE | 20.78 | 0 | 0 | 0
19 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-II Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000808/2024-2025 | 874/ND | 25/02/2025 | 20/02/2026 | S.D. CONSTRUCTION | 25.17 | 0 | 0 | 40
20 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/09450 | Augmentation | Withdrawing and Shifting of UPVC with repairing of FHTC pipeline for widening of PWD roads from Elemnagar to Hridaypur under Badlangi Padmamala Zone-II Water Supply Scheme within Chapra Block in Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000693/2024-2025 | 88/ND | 07/01/2025 | 21/02/2025 | S.S.INFRASTRUCTURE | 14.79 | 0 | 0 | 100
Total | [13 empty] | 1155.65 | 372.06 | 32.19