## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte |  |  | VCH/001049/2021-2022 | 607/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.82 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under DAKSHIN JHITKIPOTA(Z-1I) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000901/2022-2023 | 411EMD | 20/01/2023 | 19/02/2023 | M.S.C. ENTERPRISE | 14.9 | 13.74 | 92.23 | 90
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.07.2023 to 31.08.2023 (Two Month). | Assistant Engineer |  | ORD/000246/2023-2024 | 2831/ND | 28/06/2023 | 28/08/2023 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.73 | 100 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2021-2022 | 444/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.39 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 4295/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.3 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1998/ND | 08/05/2023 | 08/05/2023 | Resource Division | 0.92 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. bill for the month of Juluy under AE/EMSD-II Bhatjangla Dist Nadia |  |  | BILL/01577/2023-2024 |  | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. |  |  | BILL/00527/2023-2024 | 241/1/PFMS | 18/08/2023 | 18/08/2023 | OTHERS | 49.99 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE ALL COMPLETE BASED ON ACTUAL ESTIMATE & PROVIDING FHTC FOR DAKHIN JHITKAPOTA ZONE - II WATER SUPPLY SCHEME IN NADIA DISTRICT UNDER NADIA DIVISION. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000691/2021-2022 | 923/ND | 24/02/2022 | 25/05/2022 | SATYABRATA CHAKRABORTY | 282.53 | 120.35 | 42.6 | 68
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000050/2024-2025 | 3445/ND | 20/06/2024 | 20/07/2024 | IMAGIN | 20.46 | 5.11 | 25 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 5.78 | 16.89 | 60
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities. [Phase-II] | Assistant Engineer | Junior Engineer 2 | ORD/000661/2023-2024 | 6161/ND | 26/12/2023 | 26/06/2024 | IMAGIN | 74.48 | 11.92 | 16 | 100
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 26/10/2024 | IMAGIN | 34.21 | 0 | 0 | 100
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134, (1) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION, (2) AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION |  |  | BILL/00563/2024-2025 | 311/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 0 | 0 | 0 | 0
15 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at DAKSHIN JHITKIPOTA ZONE-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09451] | Assistant Engineer |  | ORD/000144/2025-2026 | 1145/EMD | 04/06/2025 | 02/09/2025 | M/S SAJAHAN CHOWDHURY | 38.68 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 83 m3/hr at Dakshin Jhitkipota Zone-II Water Supply Scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under Krishnagar Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000712/2023-2024 | 1320/ND | 27/02/2024 | 20/08/2025 | WIST WATER SOLUTIONS PVT LTD | 230.17 | 0 | 0 | 70
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAKSHIN JHITKIPOTA ZONE-II to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte | SM/09451 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 350 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dakshin Jhitkipota Zone-II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000168/2024-2025 | 4580/ND | 21/08/2024 | 29/03/2026 | MONDAL CONSTRUCTION | 20.42 | 0 | 0 | 30
Total | [13 empty] | 821.3 | 159.63 | 19.44