## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. |  |  | VCH/000143/2022-2023 | 06/PFMS | 26/04/2022 | 26/04/2022 | IJABUL SK. | 40.83 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district under Nadia division. |  |  | VCH/001145/2021-2022 | 718/PFMS | 30/03/2022 | 30/03/2022 | IJABUL SK. | 50 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. |  |  | VCH/001078/2021-2022 | 641/PFMS | 16/03/2022 | 16/03/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 3.6 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and construction of 400 cum capacity 20 mtr. staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 400 cum OHR of staging height 20 mtr all complete for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000662/2021-2022 | 634/ND | 10/02/2022 | 11/05/2022 | IJABUL SK. | 354.81 | 120.52 | 33.97 | 70
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Nazirpur W/S Scheme District -Nadia NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-05) | Assistant Engineer | Junior Engineer | ORD/000082/2022-2023 | 3805/EMD | 14/10/2022 | 13/11/2022 | A.K. ENTERPRISE | 13.23 | 13.23 | 100 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2021-2022 | 434/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2021-2022 | 1265/ND | 16/03/2022 | 16/03/2022 | Resource Division | 11.72 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2021-2022 | 1390/ND | 24/03/2022 | 24/03/2022 | Resource Division | 16.87 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 4313/ND | 29/09/2022 | 29/09/2022 | Resource Division | 20.05 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 76 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nazirpur to accommodate FHTC within Tehatta-I block underTehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000724/2024-2025 | 207/ND | 13/01/2025 | 12/07/2025 | TRANS ORGANICS INDIA PVT LTD | 217.81 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- III) at village Nazirpur, Bagadoba, Chhitka, Aztullanagar under Tehatta-I Block to accommodate FHTC under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000019/2025-2026 | 1805/ND | 22/04/2025 | 19/10/2025 | M/S DIPAK ENTERPRISE | 71.65 | 0 | 0 | 30
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Nazirpur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000437/2024-2025 | 7061/ND | 04/12/2024 | 03/05/2025 | BISWAS ENTERPRISE | 12.53 | 0 | 0 | 100
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NAZIRPUR to Accommodate FHTC in Tehatta-I block of Nadia district underNadia division. | SM/09452 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete & Construction of 400 CUM Capacity 20 Mtr. Staging height RCC Over Head Rservoir (including pile foundation) Pipe connection and cost of pipes, specials for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Nazirpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000019/2024-2025 | 3376/ND | 14/06/2024 | 14/06/2026 | M/S DIPAK ENTERPRISE | 217.72 | 12.26 | 5.63 | 25
Total | [13 empty] | 1032.81 | 146.01 | 14.14