## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001263/2021-2022 | 729/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.23 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Anandapur W/S Scheme, Block-Karimpur- 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 01) |  |  | ORD/000171/2022-2023 | 6182/EMD | 14/11/2022 | 14/12/2022 | H.K. DAS & CO. | 14.64 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2021-2022 | 1255/ND | 16/03/2022 | 16/03/2022 | Resource Division | 1.1 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 453/ND | 31/01/2022 | 31/01/2022 | Resource Division | 0.6 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 4312/ND | 29/09/2022 | 29/09/2022 | Resource Division | 10.92 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | LAYING OF PIPELINE UNDER PALASHIPARA PWSS FROM PALASHIPARA BAZAR TO BURNIA BUS STAND. |  |  | BILL/00527/2023-2024 | 241/1/PFMS | 18/08/2023 | 18/08/2023 | OTHERS | 49.99 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE CARRYING STRUCTURE ALL COMPLETE, PROPOSED AUGMENTATION OF RISING MAIN SYSTEM AND PROVIDING FHTC INCLUDING SUPPLYING, LAYING, FITTING, FIXING OF 15MM NB PVC (SCHEDULE 80)/20MM OD HDPE (PE100, PN16) PIPE WITH ALL NECESSARY SPECIALS, SADDLE PIECE ETC. ALL COMPLETE FOR AUGMENTATION OF GROUND BASED WATER SUPPLY SCHEME AT ANANDAPUR TO ACCOMMODATE FHTC UNDER TEHATTA SUB-DIVN UNDER NADIA DIVN, PHE DTE | Assistant Engineer | Junior Engineer 1 | ORD/000690/2021-2022 | 896/ND | 23/02/2022 | 24/05/2022 | IJABUL SK. | 205.15 | 0 | 0 | 95
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 57 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anandapur to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000093/2024-2025 | 4229/ND | 02/08/2024 | 29/01/2025 | B.M. ENGINEERING & CONSTRUCTION | 191.51 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Laying of additional pipeline for Fazilnagar Mouza and Anandapur Mouza under Fazilnagar PWSS and Anandapur PWSS under Tehatta Sub-Division under Nadia Division P.H.Engineering Dte. |  |  | ORD/000161/2024-2025 | 4904/ND | 10/09/2024 | 09/12/2024 | PATHIK PABAN NANDI | 37.63 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme (Phase- II) at Anandapur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000342/2024-2025 | 7036/ND | 29/11/2024 | 23/01/2026 | SAFTI PRIVATE LIMITED | 29.2 | 0 | 0 | 65
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground basaedpiped water supply scheme for Anandapur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000400/2024-2025 | 7124/ND | 09/12/2024 | 09/03/2025 | M/S A.K.CONSTRUCTION | 31.58 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ANANDAPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division,PHE Dte. | SM/09453 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 40
Total | [13 empty] | 621.85 | 0 | 0