## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000141/2022-2023 | 04/PFMS | 26/04/2022 | 26/04/2022 | M/S A.K.CONSTRUCTION | 0.73 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000146/2022-2023 | 01/PFMS | 26/04/2022 | 26/04/2022 | M/S A.K.CONSTRUCTION | 11.48 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-I to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000491/2021-2022 | 63/ND | 05/01/2022 | 06/03/2022 | M/S A.K.CONSTRUCTION | 33.87 | 10.03 | 29.62 | 100
4 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 7450/ND | 27/12/2021 | 27/12/2021 | Resource Division | 11.02 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000792/2023-2024 | 1904/ND | 15/03/2024 | 14/05/2024 | SUMIT GHOSH | 63.49 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Repair and renovation works of R.C.C. Elevated Reservoir 180 cum and allied works at 1st Pump House at Sonda Zone I Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000432/2023-2024 | 5591/ND | 14/12/2023 | 01/10/2024 | DAS CONSTRUCTION | 14.12 | 3.73 | 26.42 | 100
7 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer 3 | ORD/000082/2023-2024 | 2995/ND | 13/07/2023 | 01/04/2025 | TARUN KUMAR BHATTACHARYA | 62.48 | 5.5 | 8.8 | 40
8 | NADIA |  | Nadia Division | Retrofitting of Ground Water Based Piped Water Supply Scheme For Sonda I to accommodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte. | SM/09525 | Retrofitting | Construction and installation of Manifold at OHR site and allied works in connection to the Augmentation of Sonda Zone II Water Supply Scheme under Krishnagar I Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000748/2024-2025 | 495/ND | 30/01/2025 | 29/07/2025 | N.H. ENTERPRISE | 32.38 | 0 | 0 | 0
Total | [13 empty] | 229.58 | 19.26 | 8.39