## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.(Zone-I) under Elangi W/S Scheme, Block-Chapra, Dist. - Nadia. NIET No.- 18 of EE//EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001752/2022-2023 | 6187/ EMD | 14/11/2022 | 14/12/2022 | WESTERN ENGINEERING CO. | 7.76 | 7.76 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2021-2022 | 1030/ND | 03/03/2022 | 03/03/2022 | Resource Division | 4.96 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 103/ND | 06/01/2022 | 06/01/2022 | Resource Division | 2.06 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 3308/ND | 27/07/2022 | 27/07/2022 | Resource Division | 5.55 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001052/2021-2022 | 610/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.34 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete based on actual Estimate, Proposed augmentation of Rising Main system and Providing FHTC for Elangi Zone-I Water Supply Scheme in Nadia District under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000312/2023-2024 | 4284/ND | 21/09/2023 | 12/06/2025 | BALAJI UDDYOG | 204.73 | 177.26 | 86.58 | 90
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Additional Work in connection with "Shifting of existing PHE pipeline for implementation of Widening & strengthening work of Swarupganj UBI More to Anandabas Road from 0.00 Kmp to 6.10 Km under NH Divn-I RIDF-XXV within Gadigacha W/S Scheme under Krishnagar Sub-Divn under Nadia Divn, PHE Dte." | Assistant Engineer |  | ORD/000531/2022-2023 | 218/KSD | 03/03/2023 | 02/04/2023 | PAPAN ROY | 0.24 | 0.24 | 99.7 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-I Ground Based Water Supply Scheme under Chapra Block under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000335/2024-2025 | 7007/ND | 26/11/2024 | 09/06/2025 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 21.45 | 0 | 0 | 95
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Conversion of IEP to AIRP of capacity 56 Cu.m/hr at Elangi Zone-I Water Supply Scheme within Chapra Block under Nadia Divn, PHE Dte | Assistant Engineer | Junior Engineer 2 | ORD/000167/2024-2025 | 4822/ND | 05/09/2024 | 31/08/2025 | ZEOLITE FRESH INDIA | 129.41 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 250 Cu.M for Elangi Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000709/2023-2024 | 1299/ND | 23/02/2024 | 23/04/2024 | S.S.INFRASTRUCTURE | 11.25 | 10.68 | 94.89 | 95
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Repairing of Existing Boundary Wall at Head work site of Elangi Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000784/2023-2024 | 1902/ND | 15/03/2024 | 29/04/2024 | CHOWDHURY CONSTRUCTION | 6.8 | 6.77 | 99.51 | 70
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Special repair and renovation Pump House and Allied Works for 2nd Tubewell Site at Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000815/2023-2024 | 473/KlySD-II | 07/03/2024 | 06/05/2024 | M/S SANTOSHI MAA ENTERPRISE | 1.43 | 0.36 | 25.27 | 96
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Special repair and renovation Pump House and Allied Works at Head Work Site of Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000863/2023-2024 | 483/KlySD-II | 15/03/2024 | 14/05/2024 | B K ENGINEERING | 3.14 | 2.81 | 89.38 | 90
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Repairing of Existing Boundary Wall for 2nd Tubewell Site at Elangi Zone I water supply scheme in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000029/2024-2025 | 71/KlySD-II | 07/06/2024 | 06/08/2024 | SREEMA ENTERPRISE | 2.78 | 2.71 | 97.78 | 98
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 26/10/2024 | IMAGIN | 34.21 | 0 | 0 | 100
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Laying of distribution pipeline along with FHTC additionally for providing last mile connectivity to Elangi Zone-I Water Supply Scheme under in Chapra Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000670/2024-2025 | 7448/ND | 20/12/2024 | 19/05/2025 | BALAJI UDDYOG | 55.79 | 0 | 0 | 99
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Continuation of Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000050/2024-2025 | 3445/ND | 20/06/2024 | 20/07/2024 | IMAGIN | 20.46 | 5.11 | 25 | 100
18 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 2582/ND | 18/04/2024 | 18/04/2024 | Resource Division | 22.2 | 0 | 0 | 0
19 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-I to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09537 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | Assistant Engineer |  | ORD/000145/2025-2026 | 1146/EMD | 04/06/2025 | 02/09/2025 | R.N.S. TRADING | 33.06 | 0 | 0 | 0
Total | [13 empty] | 570.62 | 213.71 | 37.45