## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. |  |  | VCH/001054/2021-2022 | 612/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.69 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator(in connection with Aug. work related to FHTC) at Pump House No.I & II Z-I under Bayra W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001914/2022-2023 | 6186 EMD | 14/08/2022 | 13/09/2022 | MA ANNAPURNA ENTERPRISE | 5.47 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro- mechanical works and chlorinator etc. Rejuvention to accommodate FHTC) at Z-I under Badelangi Padmamala W/S Scheme Block Chapra under District of Nadia) | Assistant Engineer | Junior Engineer | ORD/002001/2022-2023 | 6186 / EMD | 14/08/2022 | 13/09/2022 | MA ANNAPURNA ENTERPRISE | 5.47 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 4297/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.01 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Laying of Distribution system including specials & valves,Pipe supporting structure all complete based on actual estimate & providing FHTC for Badlangi Padmamala Zone-I Water Supply Scheme in Nadia District under Nadia Division.. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000705/2021-2022 | 954/ND | 25/02/2022 | 26/05/2022 | APURBA MANDAL | 239.05 | 0 | 0 | 88
6 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Badlangi Padmamala Zone-I Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000445/2023-2024 | 6113/ND | 21/12/2023 | 15/12/2024 | CHOWDHURY & CO | 27.25 | 0 | 0 | 90
7 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-VI), under Nadia Division, P.H.E. Dte. |  | Junior Engineer 1,Junior Engineer 2 | ORD/000698/2023-2024 | 222/KLYSD-I | 09/02/2024 | 09/08/2024 | HORIZEN | 4.85 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Conversion of IEP to AIRP of capacity 62 Cu.m/hr at Badlangi Padmamala Zone-I Water Supply Scheme within Chapra block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000800/2023-2024 | 1912/ND | 15/03/2024 | 11/09/2024 | B.M. ENGINEERING & CONSTRUCTION | 174.54 | 0 | 0 | 35
9 | NADIA |  | Nadia Division | Augmentation of Ground WaterBased Piped Water Supply Scheme for BADELANGI PADMAMALA ZONE-I to Accommodate FHTC in Chapra block of Nadia district under Nadia Division,P.H.E Dte. | SM/09538 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Badlangi Padmamala Zone-I Water Supply scheme under RWS Sub Division under Nadia Division-,P.H.E Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000672/2024-2025 | 7451/ND | 20/12/2024 | 16/09/2025 | ROY ASSOCIATES | 85.97 | 0 | 0 | 25
Total | [13 empty] | 546.31 | 0 | 0