## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District |  |  | VCH/001079/2021-2022 | 642/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.49 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District |  |  | VCH/000318/2022-2023 | 37/PFMS | 27/05/2022 | 27/05/2022 | M/S TARAK CHANDRA PAUL | 144.73 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for MAHISHNENGRA ZONE I W/S scheme (for Mahisnengra, Beraberia, Tegharia, Jatrapur Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000701/2021-2022 | 963/ND | 28/02/2022 | 29/05/2022 | M/S TARAK CHANDRA PAUL | 208.33 | 62.39 | 29.95 | 98
4 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1861/ND | 26/04/2023 | 26/04/2023 | Resource Division | 26.26 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA ZONE - I W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09570 | Assistant Engineer | Junior Engineer | ORD/000131/2025-2026 | 1132/EMD | 04/06/2025 | 01/03/2026 | JAL PRAVAHIKA PVT. LTD. | 36.52 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Construction and installation of MANIFOLD and allied works at Head Works site under Mahishnengra Zone-I Ground Based Water Supply Scheme under Krishnagar-I Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | Assistant Engineer |  | ORD/000068/2025-2026 | 2400/ND | 23/05/2025 | 21/08/2025 | MAA SARADA CONSTRUCTION | 12.28 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR MAHISNENGRA ZONE - I WATER SUPPLY SCHEME in Krishnagar-I Block of Nadia District | SM/09570 | Retrofitting | Repairing of Pump house-I with sanitary arrangement under augmentation of Mahishnengra Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000209/2024-2025 | 1148/RSD | 11/09/2024 | 26/10/2024 | SUNNY ENTERPRISE | 1.88 | 0 | 0 | 90
Total | [13 empty] | 530.45 | 62.39 | 11.76