## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. |  |  | VCH/001241/2021-2022 | 725/PFMS | 30/03/2022 | 30/03/2022 | HORIZEN | 2.78 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. |  |  | VCH/001122/2021-2022 | 708/PFMS | 30/03/2022 | 30/03/2022 | SANDIP BISWAS | 60 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. |  |  | VCH/000139/2022-2023 | 01/PFMS | 26/04/2022 | 26/04/2022 | SANDIP BISWAS | 30.08 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Special repair & renovation & repair of AIRP pump house & allide works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000245/2022-2023 | 476/A/RSD | 27/07/2022 | 26/08/2022 | M/S DEBANANDA CONSTRUCTION | 1.99 | 1.97 | 98.82 | 50
5 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Providing functional household tap connection (part) including supply of 15mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Gazna Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000687/2021-2022 | 895/ND | 23/02/2022 | 24/05/2022 | SANDIP BISWAS | 143.12 | 52.49 | 36.68 | 100
6 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Special repair & renovation of head work site pump house & allied works of Gazna W/S scheme of Hanskhali block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000227/2022-2023 | 556/RSD | 30/08/2022 | 29/09/2022 | RUBI ENTERPRISE | 2.28 | 1.76 | 77.13 | 90
7 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 6909/ND | 24/11/2021 | 24/11/2021 | Resource Division | 0.68 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1873/ND | 26/04/2023 | 26/04/2023 | Resource Division | 17.01 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Supply, & Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for Mini Piped Water Supply Scheme[Gazna(part) Block-Hanskhali, Uttar Bishnupur Block-Ranaghat-II, Augmentation to Accomodate FHTC , Dist. - Nadia. under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2024-2025 | 1307/EMD | 09/05/2024 | 01/06/2025 | ORIENTAL ENGINEERING CO. | 12.61 | 0 | 0 | 45
10 | NADIA |  | Eastern Mechanical | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at GAZNA W/S Scheme Block- HANSKHALI under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09571 | Assistant Engineer |  | ORD/000149/2025-2026 | 1150/EMD | 04/06/2025 | 02/09/2025 | KARTICK BAL | 36.98 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Construction and installation of MANIFOLD and allied works at Head Works site under Gazna Ground Based Water Supply Scheme under Hanskhali Block under Nadia Division, P.H.E Dte. in connection with uniform distribution of drinking water through FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM). | Assistant Engineer |  | ORD/000221/2025-2026 | 3639/ND | 04/08/2025 | 02/11/2025 | K.K. MARKETING | 11.85 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Laying 160 mm dia UPVC pipe line inplace of damaged 160 mm dia from gazna Madhya Para to Gazna Para for smooth running of augmentation of Ground Water Supply Scheme for Gazna in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000293/2022-2023 | 5333/ND | 21/12/2022 | 07/05/2025 | SANDIP BISWAS | 17.06 | 13.69 | 80.26 | 100
13 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer | Junior Engineer 2 | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 01/07/2025 | SANDIP BISWAS | 99.5 | 70.33 | 70.69 | 100
14 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Renovation of Semi-Gravity & Semi-Pressure Type AIRP at Gazna Water Supply Scheme of capacity 58.5 Cu.m/hr. | Assistant Engineer | Junior Engineer 2 | ORD/000553/2023-2024 | 783/ND | 05/02/2024 | 05/05/2024 | APURBA MANDAL | 44.96 | 5.8 | 12.91 | 90
15 | NADIA |  | Nadia Division | RETROFITTING UNDER JAL SWAPNA FOR GAZNA PWSS in HANSKHALI Block of Nadia District under Nadia Division PHE.Dte. | SM/09571 | Retrofitting | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Gazna under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000380/2024-2025 | 1415/RSD | 19/11/2024 | 03/01/2025 | M/S KM ENTERPRISE | 2.15 | 0 | 0 | 100
Total | [13 empty] | 483.05 | 146.05 | 30.23