## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Supply, delivery and installation of voltage stabilizar under Natungram W/s scheme under EMSD II PHED. Nadia | Assistant Engineer | Junior Engineer | ORD/000325/2021-2022 | 306/EMSD II | 05/05/2021 | 14/06/2021 | SANKAR PROSAD DUTTA & CO. | 4.15 | 4.15 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division |  |  | VCH/001264/2021-2022 | 730/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.76 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division |  |  | VCH/000140/2022-2023 | 03/PFMS | 26/04/2022 | 26/04/2022 | M/S DIPAK ENTERPRISE | 0.16 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district under Nadia division |  |  | VCH/001128/2021-2022 | 714/PFMS | 30/03/2022 | 30/03/2022 | M/S DIPAK ENTERPRISE | 50 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Providing Functional Household Tap Connection (part) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (as required size), 15 mm dia Bib Cock etc. all complete at Natungram Water Supply Scheme at Hanskhali Block in Nadia District under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000673/2021-2022 | 696/ND | 15/02/2022 | 16/05/2022 | M/S DIPAK ENTERPRISE | 68.56 | 16.75 | 24.43 | 99
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2021-2022 | 443/ND | 31/01/2022 | 31/01/2022 | Resource Division | 0.6 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 4314/ND | 29/09/2022 | 29/09/2022 | Resource Division | 5.42 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1862/ND | 26/04/2023 | 26/04/2023 | Resource Division | 17.96 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Nutangram to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000705/2024-2025 | 136/ND | 08/01/2025 | 07/07/2025 | APURBA MANDAL | 160.04 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Nutangram under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000389/2024-2025 | 1425/RSD | 19/11/2024 | 16/05/2025 | SAGAR ENTERPRISE | 2.15 | 0 | 0 | 100
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under NUTANGRAM ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09572 | Assistant Engineer |  | ORD/000186/2025-2026 | 1123/EMD | 04/06/2025 | 02/09/2025 | SHRESTHA | 17.48 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NUTANGRAM to Accommodate FHTC in Hanskhali block of Nadia district underNadia division | SM/09572 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Nutangram piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000303/2024-2025 | 1276(A)RSD | 04/10/2024 | 18/11/2024 | SAGAR ENTERPRISE | 1.9 | 0 | 0 | 100
Total | [13 empty] | 331.18 | 20.9 | 6.31