## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001261/2021-2022 | 727/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.77 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Rejuenation of Kishorepur PWSS regarding FHTC in Karimpur II Block of Nadia Distric | Assistant Engineer | Junior Engineer | ORD/001929/2022-2023 | 927/EMD | 27/05/2022 | 27/03/2023 | ABHISEK ENGINEERING CONCERN | 16.28 | 16.28 | 100 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2021-2022 | 1264/ND | 16/03/2022 | 16/03/2022 | Resource Division | 2.3 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 3301/ND | 27/07/2022 | 27/07/2022 | Resource Division | 9.25 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Conversion of IEP to AIRP of capacity 60 Cu.m/hr at Kishorepur Water Supply Scheme within Karimpur-II Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000112/2024-2025 | 4343/ND | 07/08/2024 | 03/02/2025 | M/S R.K.ENTERPRISE | 129.29 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Kishorepur water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000373/2024-2025 | 7059/ND | 04/12/2024 | 04/03/2025 | M/S CHANDIMATA CONSTRUCTION | 30.07 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KISHOREPUR ground water based water supply scheme under Block_ KISHOREPUR Dist. - Nadia under EMD, PHE Dte. SM/09573 | Assistant Engineer |  | ORD/000178/2025-2026 | 1115/EMD | 04/06/2025 | 02/09/2025 | WIZARDTECH SOLUTION | 17.48 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based PipedWater Supply Scheme For KISHOREPUR to Accommodate FHTC in Karimpur-II Block of Nadia District under Nadia Division, PHE Dte. | SM/09573 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Kishorepur Ground Based Water Supply Scheme under Karimpur II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Kishorepur at Karimpur II Block by Augmentation of Ground Water based PWSS for Kishorepur Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000641/2024-2025 | 7367/ND | 18/12/2024 | 17/04/2025 | ROY ASSOCIATES | 24.03 | 0 | 0 | 0
Total | [13 empty] | 232.47 | 16.28 | 7