## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. |  |  | VCH/001068/2021-2022 | 631/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.21 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Zone-I under Dafarpota W/S Scheme, Block-Krishnagar 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (SSl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 6185/EMD | 14/11/2022 | 14/12/2022 | GHOSH AND GHOSH | 10.82 | 9.36 | 86.49 | 80
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 97/ND | 06/01/2022 | 06/01/2022 | Resource Division | 7.54 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2021-2022 | 1450/ND | 25/03/2022 | 25/03/2022 | Resource Division | 18.89 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2021-2022 | 1393/ND | 24/03/2022 | 24/03/2022 | Resource Division | 30.99 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3305/ND | 27/07/2022 | 27/07/2022 | Resource Division | 1.41 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | New Service Connection at Pump House I Zone-I under Dafarpota W/S Scheme. |  |  | BILL/02678/2023-2024 | BP-164-23-24 | 11/09/2023 | 11/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | ORD/000056/2024-2025 | 3896/ND | 16/07/2024 | 14/09/2024 | SINGHA ROY & CO. | 34.11 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Dafarpota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001399/2023-2024 | 603/EMSD-II | 22/08/2023 | 06/09/2023 | GHOSH AND GHOSH | 0.52 | 0.44 | 83.91 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Special repair and renovation of 1st Pump House and Allied Works ," and Earthwork infilling in !st Tubewell site of Dafarpota -I Water supply scheme under Krishnagar Sub-Division PHED Sl.01 | Assistant Engineer | Junior Engineer 1 | ORD/000037/2022-2023 | 512/KSD | 30/05/2022 | 29/06/2022 | DEBASHISH DEY | 3.37 | 3.12 | 92.58 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 900 CUM OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dafarpota Zone-I to accommodate FHTC within Krishnagar-1 block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000667/2021-2022 | 623/ND | 09/02/2022 | 10/05/2022 | SINGHA ROY & CO. | 253.11 | 185.88 | 73.44 | 70
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Construction and installation of Manifold and allied works at OHR site in connection to Ground Based Piped Water Supply Scheme at Dafarpota Zone II To Accommodate FHTC Within Krishnagar I Block Under Krishnanagar Sub-division Under Nadia Division,phe Dte. | Assistant Engineer |  | ORD/000102/2025-2026 | 2848/ND | 18/06/2025 | 16/09/2025 | SAHA ENGINEERS | 18.01 | 0 | 0 | 0
Total | [13 empty] | 382.56 | 198.8 | 51.97