## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. |  |  | VCH/001068/2021-2022 | 631/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.21 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Zone-I under Dafarpota W/S Scheme, Block-Krishnagar 1, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (SSl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 6185/EMD | 14/11/2022 | 14/12/2022 | GHOSH AND GHOSH | 10.82 | 0 | 0 | 80
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 97/ND | 06/01/2022 | 06/01/2022 | Resource Division | 7.54 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2021-2022 | 1450/ND | 25/03/2022 | 25/03/2022 | Resource Division | 18.89 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000139/2021-2022 | 1393/ND | 24/03/2022 | 24/03/2022 | Resource Division | 30.99 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 3305/ND | 27/07/2022 | 27/07/2022 | Resource Division | 1.41 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | New Service Connection at Pump House I Zone-I under Dafarpota W/S Scheme. |  |  | BILL/02678/2023-2024 | BP-164-23-24 | 11/09/2023 | 11/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | ORD/000056/2024-2025 | 3896/ND | 16/07/2024 | 14/09/2024 | SINGHA ROY & CO. | 34.11 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Dafarpota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001399/2023-2024 | 603/EMSD-II | 22/08/2023 | 06/09/2023 | GHOSH AND GHOSH | 0.52 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DAFARPOTA ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09574 | Augmentation | Special repair and renovation of 1st Pump House and Allied Works ," and Earthwork infilling in !st Tubewell site of Dafarpota -I Water supply scheme under Krishnagar Sub-Division PHED Sl.01 | Assistant Engineer | Junior Engineer 1 | ORD/000037/2022-2023 | 512/KSD | 30/05/2022 | 29/06/2022 | DEBASHISH DEY | 3.37 | 0 | 0 | 100
Total | [13 empty] | 111.45 | 0 | 0