## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte |  |  | VCH/001050/2021-2022 | 608/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc for Augmentation to Accommodate FHTC at Pump House No.II Zone II under Paschim Bhatjangla WS Scheme, Block Krishnagar 1, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No.- 22 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000705/2022-2023 | 6505/EMD | 01/12/2022 | 31/12/2022 | M/S. PS & ASSOCIATES | 4.38 | 0 | 0 | 90
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Paschim Bhatjangla W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 03) |  |  | ORD/002695/2022-2023 | 3912EMD | 19/10/2022 | 18/11/2022 | STANDARD ENGINEERING | 7.97 | 0 | 0 | 80
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Paschim Bhatjangla (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001404/2023-2024 | 616/EMSD-II | 24/08/2023 | 08/09/2023 | STANDARD ENGINEERING | 0.21 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 4294/ND | 29/09/2022 | 29/09/2022 | Resource Division | 1.21 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2021-2022 | 1262/ND | 16/03/2022 | 16/03/2022 | Resource Division | 1.72 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Deposit works, and new service connection under bhatjangla W/S Scheme. |  |  | BILL/03721/2023-2024 | BP-240-23-24 | 04/12/2023 | 04/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.21 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Paschim Bhatjangla Zone-II Water Supply Scheme in Krishnagar-I Block of Nadia District. | Assistant Engineer | Junior Engineer 1,Junior Engineer Krishnanagar - I Block | ORD/000496/2021-2022 | 67/ND | 05/01/2022 | 05/04/2022 | JAGANNATH ENTERPRISE | 68.71 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Banpur ii) Dakshinpara (Zone-I)iii) Dakshinpara (Zone-II) iv) Kamgachi (Zone-I)(Part-I) v)Kamgachi (Zone-I)(Part-II)vi)Kamgachi (Zone-II)(Part-I) vii) Kamgachi (Zone-II)(Part-II) | Assistant Engineer | Junior Engineer 2 | ORD/000440/2022-2023 | 246/Kly SD-I | 27/02/2023 | 27/08/2023 | HORIZEN | 4.99 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Additional Laying of UPVC Pipeline and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC pipe with all necessary specials, saddle piece etc.in connection to the Augmentation of Ground Based piped water supply scheme at Bablari-Dewanganj to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000016/2023-2024 | 1847/ND | 26/04/2023 | 25/06/2023 | A.K.ADHIKARY | 15.77 | 0 | 0 | 95
11 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Supplimentary works to completion of ongoing FHTC-related work at PH-II of Paschim Bhatjangla (Zone-II) W/S Scheme (Block - Krishnagar - I), PHE Dte., dist.- Nadia. | Assistant Engineer | Junior Engineer | ORD/002019/2023-2024 | 593/EMSD-II | 21/08/2023 | 05/09/2023 | M/S. PS & ASSOCIATES | 0.15 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 0 | 0 | 60
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Additional work of Laying Distribution System and additional work of Providing FHTC in connection with Augmentation of Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000472/2023-2024 | 147/ND | 09/01/2024 | 03/04/2025 | M/S A.K. ENTERPRISE | 33.76 | 0 | 0 | 70
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Construction Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 31.00 cum/hr at Paschim Bhatjangla water supply scheme including 3 Months Trial Run & 3 Years O&M within Krishnagar-I block under RWS Nadia Sub-division under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000707/2023-2024 | 1251/ND | 22/02/2024 | 20/08/2024 | APURBA MANDAL | 163.44 | 0 | 0 | 45
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir, Pump House, Boundary Wall and Construction of Service Road for Paschim Bhatjangla Zone-II Water Supply Scheme under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000669/2023-2024 | 6117/ND | 21/12/2023 | 13/06/2025 | KESHOB ENTERPRISE | 29.88 | 0 | 0 | 80
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for PASCHIM BHATJANGLA ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia district under Nadia division PHE Dte | SM/09575 | Augmentation | Sinking of 1 No. Big Dia Tubewell 300mm. x 200mm & 200 mtr deep by Direct Rotary Rig Method using PVC pipe & UPVC deep well screen (RDS) pipes with Ribs etc. including inter connection of Rising Main System for Paschim Bhatjangla Zone-II Water Supply Scheme at Head Work Site under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000187/2024-2025 | 5035/ND | 13/09/2024 | 28/10/2024 | ZEST INFRACON | 16.29 | 0 | 0 | 60
Total | [13 empty] | 481.73 | 0 | 0