## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) |  |  | ORD/000083/2022-2023 | 3911/EMD | 19/10/2022 | 18/11/2022 | DAS ENTERPRISE | 9.39 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Sonda-II to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000492/2021-2022 | 64/ND | 05/01/2022 | 19/02/2022 | ROY CONSTRUCTION | 15.67 | 13.4 | 85.5 | 95
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001489/2023-2024 | 687/EMSD-II | 13/09/2023 | 28/09/2023 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0 | 0 | 100
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Sonda (Zone - II) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. |  |  | ORD/002945/2022-2023 | 687/EMSD-IIDt.13/09/2023 | 14/08/2022 | 13/09/2022 | DAS ENTERPRISE (BARANAGAR) | 0.99 | 0.99 | 100 | 100
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 7452/ND | 27/12/2021 | 27/12/2021 | Resource Division | 9.44 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 4298/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.33 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Conversion of IEP to AIRP of capacity 9 Cu.m/hr at Sonda Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000792/2023-2024 | 1904/ND | 15/03/2024 | 14/05/2024 | SUMIT GHOSH | 63.49 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Repair and renovation works of R.C.C. Elevaced Reservoir 50 cum, Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Sonda Zone II Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000420/2023-2024 | 5368/ND | 04/12/2023 | 03/03/2024 | REAL TIME | 21.55 | 20.73 | 96.18 | 100
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No. I (Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.-02) |  |  | ORD/002598/2022-2023 | 3911EMD | 09/10/2022 | 08/11/2022 | DAS ENTERPRISE (BARANAGAR) | 9.39 | 8.37 | 89.06 | 0
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sonda II to accomodate FHTC in Krishnagar I Block of Nadia District under Nadia Division, PHE Dte | SM/09576 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II(Zone-II) under Sonda W/S Scheme, Block-Krishnagar 1, District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.01) | Assistant Engineer | Junior Engineer | ORD/000089/2022-2023 | 3942/EMD | 20/10/2022 | 01/03/2025 | BIJAN ENTERPRISE | 5.34 | 0 | 0 | 50
Total | [13 empty] | 136.59 | 43.48 | 31.83