## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | LAYING OF RISING MAIN AT MAHISNENGRA ZONE II WATER SUPPLY SCHEME UNDER RANAGHAT SUB DIVISION OF NADIA DIVISION, P.H.E. DTE. | Assistant Engineer |  | ORD/000689/2021-2022 | 107/RSD | 23/02/2022 | 10/03/2022 | M/S BISWAS ENTERPRISE | 1.83 | 1.42 | 77.66 | 90
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. |  |  | VCH/001080/2021-2022 | 643/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.5 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2021-2022 | 1057/ND | 04/03/2022 | 04/03/2022 | Resource Division | 3.96 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 1880/ND | 26/04/2023 | 26/04/2023 | Resource Division | 4.39 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | WBSEDCL Quotation for New Service Connection to the ongoing AIRP premises under ZONE - II of MAHISNENGRA W/S Scheme in Krishnagar - I Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004547497) |  |  | BILL/00072/2024-2025 | BP-05-24-25 | 23/04/2024 | 23/04/2024 | W.B.S.E.D.C.LTD (CHITRASALI C.C.CENTER) | 6.79 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Mahishnengra Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000291/2024-2025 | 1277/RSD | 04/10/2024 | 18/11/2024 | MANARAMA ENTERPRISE | 1.9 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Construction of 100m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Mahisnengra Zone-II PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000080/2025-2026 | 2462/ND | 27/05/2025 | 23/11/2025 | ABHAYANANDA ENTERPRISE | 8.74 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at MAHISNENGRA Zone-II W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09787 | Assistant Engineer | Junior Engineer | ORD/000133/2025-2026 | 1134/EMD | 04/06/2025 | 02/09/2025 | MAHAMAYA ENTERPRISE. | 36.66 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/09787 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Mahishnengra Zone-II Water supply scheme under Ranaghat Sub -Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000294/2024-2025 | 1279/RSD | 04/10/2024 | 18/12/2024 | REKHA ENTERPRISE | 4.45 | 1.13 | 25.31 | 100
Total | [13 empty] | 265.16 | 3.95 | 1.49