## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001071/2021-2022 | 634/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.59 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under ITLA W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000905/2022-2023 | 415/EMD | 20/01/2023 | 19/02/2023 | ANJAN ENTERPRISE | 14.53 | 13.46 | 92.63 | 80
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000128/2021-2022 | 1259/ND | 16/03/2022 | 16/03/2022 | Resource Division | 8.04 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2021-2022 | 1020/ND | 03/03/2022 | 03/03/2022 | Resource Division | 2.21 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 4323/ND | 29/09/2022 | 29/09/2022 | Resource Division | 25.29 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Itla to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000738/2021-2022 | 1313/ND | 21/03/2022 | 19/06/2022 | SHIBU BISWAS | 145.51 | 144.13 | 99.05 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ITLA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09788 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 57 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Itla PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 5 | ORD/000083/2023-2024 | 2996/ND | 13/07/2023 | 29/12/2025 | TARUN KUMAR BHATTACHARYA | 82.59 | 0 | 0 | 50
Total | [13 empty] | 281.76 | 157.59 | 55.93