## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001081/2021-2022 | 644/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.51 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Providing functional household tap connection ( Final part ) including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe line and other allied works etc all complete for JOANIA W/S scheme (for Hazrapal, Joania, Kursi, Malipota, Sardanga, Tiabali Mouza) under Ranaghat Sub Division of Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000741/2021-2022 | 1374/ND | 23/03/2022 | 21/06/2022 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 230.28 | 158.17 | 68.69 | 86
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Special repair & renovation of pump house & allied works in the premises at Pump house no-II of Joania W/S scheme of Krishnanagar-I block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000229/2022-2023 | 557/RSD | 30/08/2022 | 29/09/2022 | K.K. MARKETING | 2.62 | 2.25 | 86.2 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Special repair & renovation & repair of CWR pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000230/2022-2023 | 557/A/RSD | 30/08/2022 | 29/09/2022 | M/S ASIT ROY BHOWMIK | 2 | 1.83 | 91.38 | 90
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 4287/ND | 29/09/2022 | 29/09/2022 | Resource Division | 4.29 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1882/ND | 26/04/2023 | 26/04/2023 | Resource Division | 14.1 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Special repair & renovation of head work site pump house & allied works of Joania W/S scheme of Krishnanagar block under Ranaghat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer 1 | ORD/000228/2022-2023 | 556/A/RSD | 30/08/2022 | 29/09/2022 | ANJALI ENTERPRISE | 2.22 | 2.04 | 91.85 | 90
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at JOANIA W/S Scheme Block- Krishnagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/09789 | Assistant Engineer | Junior Engineer | ORD/000135/2025-2026 | 1136/EMD | 04/06/2025 | 02/09/2025 | M/S DILIP MITRA | 36.67 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 157/EMDdt.06.01.2023 | 08/02/2023 | 03/02/2025 | MASSK ENGINEERING WORKS | 14.9 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Providing additional functional household tap connection including repairing of existing FHTC at Joania water supply scheme under Ranaghat Sub-Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000148/2024-2025 | 654/RSD | 18/06/2024 | 14/01/2025 | ROMI TRADERS | 0.97 | 0 | 0 | 90
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JOANIA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09789 | Augmentation | Land development of Joania piped water supply scheme Head works site under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000805/2024-2025 | 200/RSD | 06/02/2025 | 21/02/2025 | APURBA MANDAL | 6.17 | 0 | 0 | 100
Total | [13 empty] | 414.71 | 164.29 | 39.62