## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab for official use for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01.01.2023 (as and when required). | Assistant Engineer | Junior Engineer 3 | ORD/000486/2022-2023 | 1331/KSD | 29/12/2022 | 29/03/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Durgapur Chowgacha to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000189/2022-2023 | 4542/ND | 21/10/2022 | 21/10/2023 | UMWELT ENGINEER PVT LTD, 140 RAJADANGA CHAKRABORTY PARA, 1ST FLOOR, KASBA, KOLKATA-700107. | 615 | 558.32 | 90.78 | 92
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000108/2021-2022 | 1032/ND | 03/03/2022 | 03/03/2022 | Resource Division | 22.03 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 2159/ND | 18/05/2022 | 18/05/2022 | Resource Division | 11.58 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2021-2022 | 1394/ND | 24/03/2022 | 24/03/2022 | Resource Division | 28.51 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 4928/ND | 25/11/2022 | 25/11/2022 | Resource Division | 11.62 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001069/2021-2022 | 632/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.43 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for JJM works for the period 90 days w.e.f. 01/04/2023.(as and when required). | Assistant Engineer |  | ORD/000591/2022-2023 | 376/KSD | 28/03/2023 | 26/06/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at Pump House No.- I & II under DURGAPUR CHOWGACHA W/S Scheme, Block- Krishnaganj , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000903/2022-2023 | 413/EMD | 20/01/2023 | 19/02/2023 | SHRESTHA | 8.93 | 7.54 | 84.46 | 99
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Durgapur Chowgacha W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001718/2023-2024 | 755/EMSD-II | 09/10/2023 | 19/10/2023 | SHRESTHA | 0.93 | 0.93 | 99.88 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000195/2022-2023 | 1003/ND | 10/03/2023 | 10/03/2023 | Resource Division | 16.45 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 2420/ND | 05/06/2023 | 05/06/2023 | Resource Division | 12.64 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 2292/ND | 29/05/2023 | 29/05/2023 | Resource Division | 24.68 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 81 m3/hr at Durgapur Chowgacha Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000785/2023-2024 | 1897/ND | 15/03/2024 | 11/09/2024 | MANGES INDUSTRIAL CORPORATION | 227.13 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Repair & Renovation of Pump House and Construction of Boundary wall and allied works at 1st and 2nd Pump House at Durgapur Chowgacha Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000475/2023-2024 | 153/ND | 09/01/2024 | 04/03/2025 | NILAY KUMAR BHATTACHARYA | 27.41 | 13.47 | 49.16 | 100
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Construction of Additional Boundary wall and allied works at Headwork Site at Durgapur Chowgacha Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000865/2024-2025 | 1474/ND | 25/03/2025 | 16/09/2026 | NILAY KUMAR BHATTACHARYA | 15.55 | 0 | 0 | 60
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Construction and installation of Manifold at OHR site, Providing leftout FHTC with laying of additional distribution system and allied works in connection to the Augmentation of Durgapur Chowgacha Water Supply Scheme under Krishnaganj Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000809/2024-2025 | 875/ND | 25/02/2025 | 25/06/2025 | M/S GHOSH CONSTRUCTION | 67.59 | 0 | 0 | 10
18 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for DURGAPUR CHOWGACHA to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division,PHE Dte. | SM/09794 | Augmentation | Pipeline Crossing by adopting Trenchless Technologies (i.e. Jack Push Method etc) and allied works for Railway in connection to the Augmentation of Ground Based Water Supply Scheme at Adityapur Village to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000176/2025-2026 | 3323/ND | 15/07/2025 | 10/07/2026 | MANGES INDUSTRIAL CORPORATION | 39.16 | 0 | 0 | 0
Total | [13 empty] | 1135.03 | 580.26 | 51.12