## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Laying of Distribution System including Specials & Valves, Pipe supporting structure all complete based on actual estimate & Providing FHTC at Murutia Water Supply Scheme in Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000704/2021-2022 | 967/ND | 28/02/2022 | 09/11/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 469.7 | 215.26 | 45.83 | 65
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2021-2022 | 1256/ND | 16/03/2022 | 16/03/2022 | Resource Division | 88.59 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 4271/ND | 29/09/2022 | 29/09/2022 | Resource Division | 27.23 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001063/2021-2022 | 621/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.44 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I under Murutia W/S Scheme, Block Karimpur-II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-03) |  |  | ORD/000886/2022-2023 | 154/EMD | 06/01/2023 | 05/02/2023 | TALUKDER & CO. | 13.64 | 13.33 | 97.7 | 20
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. III under Murutia WS Scheme, Block KarimpurII, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-05) |  |  | ORD/000888/2022-2023 | 156/EMD | 06/01/2023 | 05/02/2023 | MUKHERJEE ART CENTRE | 8.75 | 8.75 | 100 | 98
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No. II under Murutia W/S Scheme, Block Karimpur -II, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-04) | Assistant Engineer | Junior Engineer | ORD/000887/2022-2023 | 155/EMD | 06/01/2023 | 05/02/2023 | K.S.P. ENTERPRISE | 8.76 | 2.31 | 26.38 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Murutia PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer 2,Junior Engineer Karimpur- II Block | ORD/000705/2023-2024 | 1250/ND | 22/02/2024 | 11/02/2026 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 300.56 | 0 | 0 | 60
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Additional work for Laying of Di Pipe over the Murutia Bhairab River Crossing for Murutia water supply scheme in Karimpur-II Block under Tehatta Sub Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000680/2024-2025 | 7453/ND | 20/12/2024 | 18/02/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 30.01 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Murutia PWSS under Karimpur-II Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000744/2024-2025 | 422/ND | 27/01/2025 | 26/07/2025 | M/S SANJAY ADHIKARI | 29.73 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MURUTIA to Accommodate FHTC in Karimpur-II block of Nadia District under Nadia Division, PHE Dte. | SM/09798 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | Assistant Engineer | Junior Engineer 2 | ORD/000790/2024-2025 | 762/ND | 19/02/2025 | 20/05/2025 | DEBASIS SAMADDAR | 74.08 | 0 | 0 | 0
Total | [13 empty] | 1055.49 | 239.65 | 22.7