## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000451/2022-2023 | 67/PFMS | 28/06/2022 | 28/06/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 87.34 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001070/2021-2022 | 633/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.99 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I & II under Krishnaganj Majdia W/S Scheme, Block- Krishnaganj, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000194/2022-2023 | 6188/EMD | 14/11/2022 | 14/12/2022 | S.G. TECHNICAL SERVICES | 12 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | Assistant Engineer |  | ORD/000410/2023-2024 | 800/KSD | 16/06/2023 | 16/09/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000112/2021-2022 | 1023/ND | 03/03/2022 | 03/03/2022 | Resource Division | 11.25 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 450/ND | 31/01/2022 | 31/01/2022 | Resource Division | 3.58 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2021-2022 | 1257/ND | 16/03/2022 | 16/03/2022 | Resource Division | 16.73 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 103 m3/hr at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000776/2023-2024 | 1892/ND | 15/03/2024 | 11/09/2024 | B.M. ENGINEERING & CONSTRUCTION | 266.82 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Krishnaganj Majdia to accommodate FHTC within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000703/2021-2022 | 966/ND | 28/02/2022 | 29/05/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 495.71 | 0 | 0 | 82
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 450 cum, Repair & Renovation of Pump House, Store, Guard Room, Boundary wall and allied works at 1st and 2nd Pump House at Krishnaganj Majhdia Water Supply Scheme within Krishnaganj block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000391/2023-2024 | 5123/ND | 17/11/2023 | 15/02/2024 | CHOWDHURY & CO. | 34.94 | 0 | 0 | 98
11 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Krishnaganj Majdia W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 1659/CDD | 17/10/2023 | 14/04/2024 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Construction of Pump House (3.6mtr. X 3.0 mtr.) and Boundary Wall at 3rd T/W site for Krishnaganj Majhdia water supply scheme under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000008/2024-2025 | 3262/ND | 10/06/2024 | 25/07/2024 | D.K. CONSTRUCTION | 17.11 | 0 | 0 | 80
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | WBSEDCL SUPPLEMENTARY Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application ID. 100000120534) |  |  | BILL/01891/2024-2025 | BP-164-24-25 | 25/11/2024 | 25/11/2024 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 3.49 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly constructed Pump House No. - III under KRISHNAGANJ MAJDIA W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004847470) |  |  | BILL/01476/2024-2025 | BP-88-24-25 | 28/08/2024 | 28/08/2024 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 0.56 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Construction and installation of Manifold and allied works at OHR site in connection to Retrofitting (Phase-I) Under JJM In Ground Based Piped Water Supply Scheme at Krishnaganj Majhdia To Accommodate FHTC Within Krishnaganj Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000749/2024-2025 | 496/ND | 30/01/2025 | 26/11/2025 | CHOWDHURY & CO. | 39.44 | 0 | 0 | 0
16 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte. | SM/09799 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Krishnaganj Majhdia ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/09799 | Assistant Engineer |  | ORD/000175/2025-2026 | 1108/EMD | 04/06/2025 | 02/09/2025 | S.P. ENTERPRISE (KOLKATA) | 20.79 | 0 | 0 | 0
Total | [13 empty] | 1033.83 | 0 | 0