## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Repairing and renovation of pump house, compressor room , boundary , extension of drain & other allied works at Ber ramchandrapur pump house no: 1 under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000111/2022-2023 | 676/ Kly SD-I | 26/07/2022 | 25/08/2022 | CHOWDHURY & CO. | 4 | 3.99 | 99.75 | 100
2 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 120 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR BERRAMCHANDRAPUR ZONE-I W/S SCH (2ND TUBE WELL SITE), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000164/2022-2023 | 375/CMSD-I | 05/08/2022 | 20/08/2022 | UNIVERSAL ENTERPRISES | 3.7 | 3.7 | 100 | 0
3 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | PROVIDING 300MM & 200MM NOMNAL DIA UPVC PIPE CONFORMING TO IS 12818:2010 & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL) W/S SCH, KARIMPUR BLOCK UNDER NADIA DISTRICT CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000165/2022-2023 | 376/CMSD-I | 05/08/2022 | 20/08/2022 | UNIVERSAL ENTERPRISES | 3.8 | 3.8 | 100 | 0
4 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | SUPPLY & DELIVERY PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BERRAMCHANDRAPUR ZONE-I (2ND TUBE WELL SITE) W/S SCH, KARIMPUR BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000166/2022-2023 | 377/CMSD-I | 05/08/2022 | 20/08/2022 | UNIVERSAL ENTERPRISES | 2.07 | 1.7 | 82.03 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001062/2021-2022 | 620/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.78 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Laying of distribution system including specials, Valves & Pipe supporting structure all complete based on actual estimate & providing FHTC for Ber Ramchandrapur Zone-I Water Supply Scheme in Nadia District under Nadia Division. | Assistant Engineer |  | ORD/000725/2021-2022 | 1207/ND | 14/03/2022 | 12/06/2022 | SANDIP BISWAS | 115.92 | 115.91 | 99.99 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Repairing and renovation of pump house, dismantling part of boundary wall & re - construction it, land development , & construction of bath room with other allied works at Ber ramchandrapur pump house no: II under Ber ramchandrapur zone:1 Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000112/2022-2023 | 677/ Kly SD-I | 26/07/2022 | 25/08/2022 | RAJAT ENTERPRISE | 4.98 | 4.98 | 99.94 | 100
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under BERRAMCHANDRAPUR (Zone-I) W/S Scheme, Block- Karimpur-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer |  | ORD/000899/2022-2023 | 409/EMD | 20/01/2023 | 19/02/2023 | SHIVAM ENTERPRISE | 15.53 | 14.87 | 95.76 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2021-2022 | 1263/ND | 16/03/2022 | 16/03/2022 | Resource Division | 5.58 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2021-2022 | 1033/ND | 03/03/2022 | 03/03/2022 | Resource Division | 4.64 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 2506/ND | 08/06/2022 | 08/06/2022 | Resource Division | 2.86 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Conversion of IEP to AIRP of capacity 32 Cu.m/hr at Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000796/2023-2024 | 1908/ND | 15/03/2024 | 13/07/2024 | M/S R.K.ENTERPRISE | 124.95 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and allied works at Ber Ramchandrapur Zone-I Water Supply Scheme, Karimpur-I Block, Nadia. | Assistant Engineer |  | ORD/000303/2022-2023 | 1162/Kly SD-1 | 16/12/2022 | 31/12/2022 | SANDIP BISWAS | 0.95 | 0.95 | 99.87 | 100
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Ber Ramchandrapur Z-I Water Supply Scheme Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000675/2023-2024 | 1174/ND | 21/02/2024 | 15/02/2025 | REAL TIME | 32.25 | 19.88 | 61.64 | 75
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09811 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Ber Ramchandrapur Zone-I PWSS within Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000770/2023-2024 | 1760/ND | 12/03/2024 | 23/10/2024 | CHINMOY BISWAS | 16.86 | 4.46 | 26.47 | 100
Total | [13 empty] | 340.88 | 174.24 | 51.11