## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Repairing and renovation of pump house, Dismantling of boundary wall & re-construction , & construction of bath room with other allied works at Uttar tajpur pump house no: II under Uttar tajpur W/S, Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000114/2022-2023 | 679/ Kly SD-I | 26/07/2022 | 25/08/2022 | K.K. MARKETING | 4.99 | 4.99 | 99.92 | 100
2 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR P/W SCHEME (REPLACEMENT TW-III), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000077/2022-2023 | 279/CMSD-II(D) | 01/06/2022 | 16/06/2022 | OSMAN SEKH | 4.39 | 4.05 | 92.39 | 0
3 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MMX200MMX250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III), KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II(D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000078/2022-2023 | 276/CMSD-II(D) | 01/06/2022 | 29/10/2118 | OSMAN SEKH | 3.52 | 1.85 | 52.49 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Repairing and renovation of pump house, extension of boundary wall , & construction of drain with other allied works at Uttar tajpur pump house no: I under Uttar tajpur W/S , Karimpur -I under Kalyani Sub-Div-I, Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000113/2022-2023 | 678/Kly SD-I | 26/07/2022 | 25/08/2022 | S.M. ENTERPRISE | 4.83 | 4.83 | 99.96 | 100
5 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000075/2022-2023 | 285/CMSD-II(D) | 01/06/2022 | 16/06/2022 | OSMAN SEKH | 2.07 | 1.63 | 78.79 | 0
6 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | PROVIDING 200 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S SCHEME (REPLACEMENT TW-III) KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000076/2022-2023 | 278/CMSD-II(D) | 01/06/2022 | 16/06/2022 | OSMAN SEKH | 4.44 | 0.79 | 17.85 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Interconnection of newly sunk tubewell at 2nd Pump House including cleaning of rising main and delivery pipeline of Utter Tajpur Water Supply Scheme, Karimpur-I Block, Nadia. | Assistant Engineer |  | ORD/000161/2022-2023 | 873/Kly SD-I | 20/09/2022 | 05/10/2022 | M/S SHAIKH ENTERPRISE | 1 | 1 | 99.94 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001065/2021-2022 | 623/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.13 | 0 | 0 | 0
9 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000434/2022-2023 | 1350/CDD | 24/11/2022 | 24/12/2022 | PADMA ENGINEERING & CO. | 18.38 | 3.67 | 19.97 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete based on actual Estimate & Providing FHTC for Uttar Tajpur water supply scheme in Nadia District under Nadia Division | Assistant Engineer |  | ORD/000730/2021-2022 | 1246/ND | 16/03/2022 | 14/06/2022 | M/S MALLICK ENTERPRISE | 167.79 | 167.77 | 99.99 | 100
11 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Continuation for hiring of diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the DIC, CMSD-II(D), CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000304/2022-2023 | 549/CMSD-II(D) | 19/12/2022 | 26/12/2022 | ASHUTOSH PAL | 0.28 | 0.28 | 100 | 0
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Supply delivery & installation of submersible pumping machinery and allied works for newly sunk Tube well (replacement) at PH No. II in connection with ongoing FHTC works by Civil wing under Uttar Tajpur PWSS Dist. Nadia | Assistant Engineer | Junior Engineer | ORD/001930/2022-2023 | 196/EMSD II | 29/07/2022 | 29/03/2023 | T.N. BANERJEE | 3 | 3 | 100 | 100
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000124/2021-2022 | 1252/ND | 16/03/2022 | 16/03/2022 | Resource Division | 1.18 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000107/2021-2022 | 1029/ND | 03/03/2022 | 03/03/2022 | Resource Division | 4.4 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000010/2023-2024 | 1806 / ND | 24/04/2023 | 23/07/2023 | APURBA MANDAL | 85.67 | 0 | 0 | 60
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Providing FHTC including Laying Distribution System in connection with J.J.M. Work under village Madhugari to cover up left out portion under Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000423/2024-2025 | 7165/ND | 10/12/2024 | 06/10/2025 | S.S. ENTERPRISE | 58.08 | 0 | 0 | 65
17 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II, under Uttartajpur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. [SM/09812] | Assistant Engineer | Junior Engineer | ORD/000338/2024-2025 | 2153/EMD | 30/08/2024 | 31/08/2025 | RAJ & ENTERPRISE | 14.54 | 0 | 0 | 80
18 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Uttartajpur PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer Karimpur- II Block | ORD/000745/2024-2025 | 423/ND | 27/01/2025 | 22/05/2026 | NISHITH BANERJEE | 26.22 | 0 | 0 | 100
19 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for UTTAR TAJPUR to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09812 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer Karimpur- II Block | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 07/04/2026 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 40
Total | [13 empty] | 454.22 | 193.86 | 42.68