## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001057/2021-2022 | 615/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.16 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) |  |  | ORD/001157/2023-2024 | 1503EMD | 18/04/2023 | 18/05/2023 | MA ANNAPURNA ENTERPRISE | 11.19 | 5.03 | 44.98 | 60
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Different Electro-Mechanical Extra works for completion FHTC Augmentation works at Elangi Zone-II and Ghoralia Zone-II under EMSD-III,P.H.E.Dte. Dist-Nadia. | Assistant Engineer | Junior Engineer | ORD/001504/2023-2024 | 759/EMSD-III | 24/07/2023 | 08/08/2023 | MA ANNAPURNA ENTERPRISE | 0.32 | 0.32 | 100 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2021-2022 | 1250/ND | 16/03/2022 | 16/03/2022 | Resource Division | 0.86 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 4315/ND | 29/09/2022 | 29/09/2022 | Resource Division | 2.17 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 3791/ND | 24/08/2023 | 24/08/2023 | Resource Division | 1.54 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Laying Of Distribution System including Specials, Valves & Pipe Supporting Structure All Complete Based On Actual Estimate & Providing FHTC for Elangi ZONE - II Water Supply Scheme in Nadia District under Nadia Division PHE Dte.. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000702/2021-2022 | 965/ND | 28/02/2022 | 09/11/2025 | MADE & TRADE CO. | 310.84 | 94.7 | 30.46 | 46
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipment and allied works at ELANGI ZONE-II W/S Scheme Block- Chapra under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. [SM/09813] | Assistant Engineer |  | ORD/000145/2025-2026 | 1146/EMD | 04/06/2025 | 02/09/2025 | R.N.S. TRADING | 33.06 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Conversion of IEP to AIRP of capacity 36 Cu.m/hr at Elangi Zone-II Water Supply Scheme within Chapra Block block under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer |  | ORD/000887/2024-2025 | 1557/ND | 28/03/2025 | 24/09/2025 | APURBA MANDAL | 129.36 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Laying of dedicated pipeline for Pipragachhi and part of Elangi Mouza for augmentation of Elangi Water Supply Scheme in Chapra Block, Nadia under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000010/2025-2026 | 1773/ND | 21/04/2025 | 18/10/2025 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 86.27 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for ELANGI ZONE-II to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte. | SM/09813 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Elangi Zone-II PWSS under Chapra Block under Tehatta Sub- Division,P.H.E Dte. | Assistant Engineer | Junior Engineer Chapra Block | ORD/000743/2024-2025 | 421/ND | 27/01/2025 | 24/09/2025 | M/S DIPAK ENTERPRISE | 73.39 | 0 | 0 | 40
Total | [13 empty] | 652.15 | 100.05 | 15.34