## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001058/2021-2022 | 616/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.71 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Ber Ramchandrapur W/S Scheme, Block-Karimpur-I, District of Nadia. NIET No. 14 of EE/EMD of 2022-23 (Sl. No. -06) |  |  | ORD/000090/2022-2023 | 3943/EMD | 20/10/2022 | 19/11/2022 | MAA TARA CONSTRUCTION | 8.2 | 0 | 0 | 70
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2021-2022 | 1026/ND | 03/03/2022 | 03/03/2022 | Resource Division | 2.13 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000127/2021-2022 | 1261/ND | 16/03/2022 | 16/03/2022 | Resource Division | 1.44 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I(Zone-II) under Berramchandrapur W/S Scheme, Block-Karimpur- 1,District of Nadia. NIET No.- 14 of EE/EMD of 2022-23 (Sl. No.- 05) | Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 3913/EMD | 19/10/2022 | 18/11/2022 | C.M.S. ENGINEERING CONCERN. | 10.73 | 0 | 0 | 97
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Providing FHTC by Augmentation under jal swapna for Ber Ramchandrapur Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- I Block,Junior Engineer Karimpur- II Block | ORD/000674/2021-2022 | 694/ND | 15/02/2022 | 16/05/2022 | SUDHAMAY MAJUMDAR | 77.58 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Additional work of Laying Distribution System and additional work of providing FHTC in connection with Augmentation of Ber Ramchandrapur Zone-II PWSS within Karimpur-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000778/2023-2024 | 1763/ND | 12/03/2024 | 06/05/2025 | MALI CONSTRUCTION | 38.98 | 0 | 0 | 80
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Conversion of IEP to AIRP of capacity 30 Cu.m/hr at Ber Ramchandrapur Zone-II Water Supply Scheme within Karimpur-I block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000797/2023-2024 | 1909/ND | 15/03/2024 | 05/11/2025 | ASIT PRAMANIK | 124.74 | 0 | 0 | 80
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09814 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) for Ber Ramchandrapur Z-II Water Supply Scheme Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000170/2024-2025 | 4579/ND | 21/08/2024 | 12/02/2026 | MONDAL CONSTRUCTION | 22.28 | 0 | 0 | 80
Total | [13 empty] | 288.8 | 0 | 0