## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001055/2021-2022 | 613/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.52 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Laying of distribution system including specials,valves & pipe supporting structure all complete based on actual estimate & Providing FHTC for Muktadaha Zone-I Water Supply Scheme under Nadia Division. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000740/2021-2022 | 1314/ND | 21/03/2022 | 19/06/2022 | UMWELT ENGINEERS PVT LTD | 257.59 | 228.85 | 88.84 | 95
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2021-2022 | 1254/ND | 16/03/2022 | 16/03/2022 | Resource Division | 10.25 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 4286/ND | 29/09/2022 | 29/09/2022 | Resource Division | 9.62 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000025/2023-2024 | 1783/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 0 | 0 | 90
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Quotation for Load enhacement charges and security deposit for Muktadaha Zone- 1, PH- 1 site. |  |  | BILL/01778/2024-2025 | BP-143-24-25 | 28/10/2024 | 28/10/2024 | W.B.S.E.D.C.L (KARIMPUR C.C.C) | 0.18 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Mukatadaha Zone-I PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000762/2024-2025 | 425/ND | 27/01/2025 | 23/11/2025 | GOPAL KIRTYANIYA | 32.88 | 0 | 0 | 95
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 40
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Muktadaha Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/09815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division, P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000297/2025-2026 | 3336/ND | 15/07/2025 | 11/01/2026 | THE TOWER CONSTRUCTION | 31.3 | 0 | 0 | 20
Total | [13 empty] | 626.5 | 228.85 | 36.53