## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001056/2021-2022 | 614/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.57 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | laying of distribution pipe line including supply of 63mm dia UPVC pipe at Fazlnagar W/S scheme under Nadia Division P.H.E. Directorate. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000318/2021-2022 | 1191/PH | 03/12/2021 | 13/12/2021 | A.P. POWER & CONCRETE | 0.61 | 0.57 | 93.21 | 100
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II (Zone-II) under Muktadaha W/S Scheme in Karimpur-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-02) |  |  | ORD/000079/2022-2023 | 3802/EMD | 14/10/2022 | 13/11/2022 | AMIT DAS | 5.96 | 5.96 | 100 | 90
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accommodate FHTC at Pump House No.I Zone II under Muktadaha WS Scheme, Dist. Nadia under Eastern Mechanical Division, PHE Dte. NIET No. 22 OF EE/EMD OF 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000704/2022-2023 | 6504/EMD | 01/12/2022 | 31/12/2022 | WESTERN ENGINEERING CO. | 10.49 | 9.54 | 90.94 | 100
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000148/2021-2022 | 1449/ND | 25/03/2022 | 25/03/2022 | Resource Division | 9.36 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 452/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.56 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000123/2021-2022 | 1251/ND | 16/03/2022 | 16/03/2022 | Resource Division | 1.42 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 4299/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.79 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Providing FHTC by Augmentation under jal swapna for Muktadaha Zone-II Water Supply scheme in Karimpur-I block of Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000672/2021-2022 | 695/ND | 15/02/2022 | 16/04/2022 | M/S KRISHNA MONDAL | 43.92 | 43.9 | 99.96 | 99
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000769/2023-2024 | 1821/ND | 14/03/2024 | 14/04/2024 | IMAGIN | 34.21 | 9.67 | 28.27 | 60
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000254/2024-2025 | 6305/ND | 26/09/2024 | 26/10/2024 | IMAGIN | 34.21 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 m3/hr capacity for Augmentation of Ground Based Water Supply Scheme at Muktadaha Zone-II including 3 Months Trial Run & 3 Years O&M to accommodate FHTC under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer Karimpur- II Block | ORD/000737/2023-2024 | 1493/ND | 04/03/2024 | 22/02/2026 | MONDAL PRECISION PRIVATE LIMITED | 162.44 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House and allied works for Muktadaha Zone-II PWSS and Murutia PWSS within Karimpur-I Block and Karimpur-II Block Under Tehatta Sub-Division under Nadia Division P.H.E. | Assistant Engineer |  | ORD/000790/2024-2025 | 762/ND | 19/02/2025 | 20/05/2025 | DEBASIS SAMADDAR | 74.08 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 40
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MUKTADAHA ZONE-II to Accommodate FHTC in Karimpur-I block of Nadia District under Nadia Division, PHE Dte. | SM/09816 | Augmentation | Construction of RCC Over Head Elevated Reservoir in connection with providing FHTC by augmentation under Jal Swapna for Muktadaha Zone-II Water Supply Scheme in Karimpur-I Block under RWS Nadia Sub-Divn. of Nadia District. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer Karimpur- II Block,Junior Engineer Tehatta - II Block | ORD/000739/2021-2022 | 1342/ND | 22/03/2022 | 05/01/2025 | K.P. CONSTRUCTION | 48.71 | 31.37 | 64.41 | 95
Total | [13 empty] | 509.53 | 101.01 | 19.82