## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 mtr , Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Hudachapra Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000732/2021-2022 | 1288/ND | 17/03/2022 | 16/05/2022 | USHA CONSTRUCTION | 59.49 | 53.62 | 90.14 | 95
2 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 4285/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.52 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte |  |  | VCH/001242/2021-2022 | 726/PFMS | 30/03/2022 | 30/03/2022 | HORIZEN | 2.47 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Providing Left-out Functional Household tap Connection including supply of 15mm dia PVC pipe of average length of 15 mtr along with laying of different dia UPVC pipe and other allied works etc. all complete for augmentation of Huda Chapra W/S Scheme under Ranaghat Sub-Division of Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000296/2023-2024 | 924/RSD | 14/09/2023 | 14/10/2023 | USHA CONSTRUCTION | 4.95 | 4.89 | 98.75 | 100
5 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1868/ND | 26/04/2023 | 26/04/2023 | Resource Division | 19.29 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hudachapra to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000106/2024-2025 | 4282/ND | 05/08/2024 | 31/07/2025 | MANGES INDUSTRIAL CORPORATION | 160.4 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 19.16 | 19.96 | 81
8 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Huda Chapra under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000381/2024-2025 | 1417/RSD | 19/11/2024 | 03/01/2025 | GITARANI ENTERPRISE | 2.15 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Hudachapra piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000176/2024-2025 | 1141/RSD | 11/09/2024 | 26/10/2024 | GITARANI ENTERPRISE | 1.9 | 0 | 0 | 100
10 | NADIA |  | Eastern Mechanical | Providing FHTC by Augmentation under Jal Swapna for HUDA CHAPRA Piped Water Supply Scheme in Hanskhali block of Nadia district under Nadia Division, PHE Dte | SM/09817 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under HUDA CHAPRA ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. SM/09817 | Assistant Engineer |  | ORD/000179/2025-2026 | 1116/EMD | 04/06/2025 | 02/09/2025 | P.K. ENTERPRISE | 17.48 | 0 | 0 | 0
Total | [13 empty] | 364.66 | 77.67 | 21.3