## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer etc. for Augmentation to Accomodate FHTC at Pump House No.II under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET NO.- 13 of EE/EMD of 2022-23 (Sl. No.-04) |  |  | ORD/000081/2022-2023 | 3804/EMD | 14/10/2022 | 13/11/2022 | BISALAXMI ENTERPRISE | 6.12 | 6.02 | 98.38 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Laying of Distribution system including specials, valves & pipe supporting structure all complete based on actual estimate & providing FHTC for Senpur Water supply Scheme in Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000711/2021-2022 | 1065/ND | 04/03/2022 | 02/06/2022 | RADIANT | 388.55 | 295.38 | 76.02 | 80
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electrio-Mechanical works, Voltage Stabilizer and Automatic Chlorinator etc. for Augmentation to Accomodate FHTC at Pump House No.I under Senpur W/S Scheme in Krishnagar-I Block of Nadia District. NIET No.- 13 of EE/EMD of 2022-23 (Sl. No.-03) |  |  | ORD/000080/2022-2023 | 3803/EMD | 14/10/2022 | 13/11/2022 | S.S.ENTERPRISES | 10.65 | 9.26 | 86.97 | 10
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2021-2022 | 1021/ND | 03/03/2022 | 03/03/2022 | Resource Division | 15.96 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/001064/2021-2022 | 622/PFMS | 14/03/2022 | 14/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.12 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000028/2023-2024 | 1786/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 41.65 | 17.78 | 57
7 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-II of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001405/2023-2024 | 598/EMSD-II | 22/08/2023 | 06/09/2023 | BISALAXMI ENTERPRISE | 0.27 | 0.26 | 96.68 | 100
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I of Senpur W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001715/2023-2024 | 753/EMSD-II | 09/10/2023 | 19/10/2023 | S.S.ENTERPRISES | 0.88 | 0.84 | 96.1 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Additional work of Laying of pipe line including providing FHTC and all allied work in connection with Augmentation of Senpur PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000172/2024-2025 | 5036/ND | 13/09/2024 | 05/06/2026 | ROY ASSOCIATES | 56.45 | 0 | 0 | 20
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Repair and Renovation Works of OHR, Boundary Wall at Head Work Site and Tube Well Site, Pump House at Head Work Site and Tube Well Sites, Contruction of Service Road at Head Work Site of Senpur Water Supply Scheme within Krishnagar -I Block under RWS Nadia Sub-Division under Nadia Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000233/2024-2025 | 6410/ND | 01/10/2024 | 09/05/2026 | M/S INDUSTRIAL CONSTRUCTION | 29.02 | 0 | 0 | 50
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Renovation of Settling Tank including construction of column and RCC wall inside the Settling Tank in Senpur Water Supply Scheme under RWS Nadia Sub Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000070/2024-2025 | 3989/ND | 22/07/2024 | 20/09/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 17.12 | 16.95 | 99.02 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site of Senpur Piped Water Supply Scheme under RWS Nadia Sub Division, Nadia, P.H.E Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000299/2024-2025 | 6757/ND | 11/11/2024 | 10/01/2025 | B.S. ENTERPRISE | 24.86 | 0 | 0 | 60
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | WBSEDCL's Quotation of New Service Connection in Bulk Contract Demand to the Head Work Site under Senpur W/S Scheme in Krishnagar - I Block, PHE Dte., Dist.- Nadia. (Application No. 3004752314) |  |  | BILL/00726/2024-2025 |  | 18/06/2024 | 18/06/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System at Shimultala village within Krishnanagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000105/2025-2026 | 2851/ND | 18/06/2025 | 15/11/2025 | SANDIP BISWAS | 46.75 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Senpur to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | SM/10009 | Augmentation | Construction Of Chlorine storage Room (2m X 2m) At H/w Site of 13nos PWSS Under RWS Nadia Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer Chapra Block,Junior Engineer Karimpur- II Block,Junior Engineer Krishnanagar - I Block | ORD/000107/2025-2026 | 2853/ND | 18/06/2025 | 17/08/2025 | ANJALI ENTERPRISE | 10.53 | 0 | 0 | 0
Total | [13 empty] | 848.96 | 370.36 | 43.63