## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 700 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials. and Soil investigation for construction of one new 700 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Dignagar to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000071/2022-2023 | 1648/ND | 06/04/2022 | 01/01/2027 | TARUN KUMAR BHATTACHARYA | 923.7 | 426 | 46.12 | 53
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2021-2022 | 1391/ND | 24/03/2022 | 24/03/2022 | Resource Division | 32.81 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 377/ND | 27/01/2022 | 27/01/2022 | Resource Division | 32.97 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 379/ND | 27/01/2022 | 27/01/2022 | Resource Division | 50.46 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 4311/ND | 29/09/2022 | 29/09/2022 | Resource Division | 35.85 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme |  |  | VCH/001074/2021-2022 | 637/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.38 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Continuation of Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-08-2023 to 31-01-2024= 184 days. | Assistant Engineer | Junior Engineer 2 | ORD/000257/2023-2024 | 736/RSD | 28/07/2023 | 28/01/2024 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.22 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Dignagar water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10019) | Assistant Engineer | Junior Engineer 3 | ORD/000033/2023-2024 | 2101/ND | 15/05/2023 | 30/09/2024 | JOY HIND TUBEWELL'S | 29.87 | 12.47 | 41.76 | 100
9 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DIGNAGAR W/S Scheme, Block-Krishnagar-I , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000902/2022-2023 | 412/EMD | 20/01/2023 | 16/02/2025 | M/S GHOSH ENTERPRISE | 16.13 | 0 | 0 | 80
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Dignagar Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000502/2023-2024 | 5559/ND | 12/12/2023 | 10/02/2024 | DEY ENTERPRISE | 12.15 | 9.7 | 79.85 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Conversion of IEP to AIRP of capacity 132 Cu.m/hr at Dignagar Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000795/2023-2024 | 1907/ND | 15/03/2024 | 01/09/2026 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 208.9 | 62.61 | 29.97 | 50
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | WBSEDCL's Quotation for New Service Connection charges to the newly constructed Pump House - III of Dignagar W/S Scheme in Krishnagar-I Block, Dist- Nadia. (Application No. 3004728299) |  |  | BILL/00727/2024-2025 | BP-50-24-25 | 21/06/2024 | 21/06/2024 | W.B.S.E.D.C.LTD (DIGNAGAR C.C.C) | 8.4 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Dignagar W/S Scheme Block- Krishnanagar-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/10019 | Assistant Engineer | Junior Engineer | ORD/000138/2025-2026 | 1139/EMD | 04/06/2025 | 02/09/2025 | INDIA ENTERPRISE | 51.72 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | Construction and installation of Manifold and allied works at OHR site in connection to Retrofitting (Phase-I) Under JJM In Ground Based Piped Water Supply Scheme at Itla To Accommodate FHTC Within Krishnagar I Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000862/2024-2025 | 1471/ND | 25/03/2025 | 24/05/2025 | NISHITH BANERJEE | 19.82 | 0 | 0 | 90
15 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | WBSEDCL Quotation for New Service Connection to Enhance Contract Demand at P/H-2 of Dignagar PWSS, P.H.E. Dte. in Krishnanagar-I Block, Dist.- Nadia. (Application No.: 3005447548) |  |  | BILL/02799/2025-2026 |  | 08/12/2025 | 08/12/2025 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 4.25 | 0 | 0 | 0
16 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme | SM/10019 | Augmentation | WBSEDCL QUOTATION for 11 KV HTOH Shifting works to Head Work Site under DIGNAGAR PWSS in KRISHNAGAR-1 BLOCK, Dist.- NADIA. (Application ID: 100000130754) |  |  | BILL/03273/2024-2025 | BP-281 | 27/03/2025 | 27/03/2025 | W.B.S.E.D.C.LTD (DIGNAGAR C.C.C) | 3.4 | 0 | 0 | 0
Total | [13 empty] | 1438.03 | 510.79 | 35.52