## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Laying of Distribution System including specials, valves & pipe Supporting structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 400 CUM OHR , all complete for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000003/2022-2023 | 1956/ND | 28/04/2022 | 08/04/2026 | M/S S.S ENTERPRISE | 601.69 | 278.85 | 46.34 | 90
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2021-2022 | 1253/ND | 16/03/2022 | 16/03/2022 | Resource Division | 19.78 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 445/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2021-2022 | 1019/ND | 03/03/2022 | 03/03/2022 | Resource Division | 22.52 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 2507/ND | 08/06/2022 | 08/06/2022 | Resource Division | 4.25 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000145/2021-2022 | 1392/ND | 24/03/2022 | 24/03/2022 | Resource Division | 16.87 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 3307/ND | 27/07/2022 | 27/07/2022 | Resource Division | 30.17 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. |  |  | VCH/000519/2022-2023 | 87/PFMS | 22/07/2022 | 22/07/2022 | M/S S.S ENTERPRISE | 187.3 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. |  |  | VCH/001262/2021-2022 | 728/PFMS | 30/03/2022 | 30/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.09 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 83 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Betai Zone-II to accommodate FHTC under Tehatta Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000155/2024-2025 | 4350/ND | 07/08/2024 | 03/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 227.43 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Collection of Household data through mobile app for FHTC Connection (Phase-III), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000695/2023-2024 | 209/KLYSD-I | 09/02/2024 | 09/08/2024 | TECHVISION | 4.86 | 4.86 | 100 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Construction of Boundary wall at Head Work Site and 2nd Tube Well Site of Betai Zone-II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000753/2023-2024 | 1628/ND | 07/03/2024 | 02/03/2025 | NAMDAR ALI | 21.11 | 0 | 0 | 12
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-I ground water based water supply scheme under Block_Tehatta-I Dist. - Nadia under EMD, PHE Dte. SM/10414 |  |  | ORD/000194/2025-2026 | 1119/EMD | 04/06/2025 | 02/09/2025 | MA ANNAPURNA ENTERPRISE | 24.48 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BETAI ZONE-II to Accommodate FHTC in Tehatta-I Block of Nadia District under Nadia Division,PHE Dte. | SM/10034 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Betai Zone-II ground water based water supply scheme under Block_Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/10034 | Assistant Engineer |  | ORD/000183/2025-2026 | 1120/EMD | 04/06/2025 | 02/09/2025 | M/S CHANDIMATA ELECTRICALS | 24.48 | 0 | 0 | 0
Total | [13 empty] | 1191.01 | 283.7 | 23.82