## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte |  |  | VCH/001067/2021-2022 | 630/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.11 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period of 90 days w.e.f 01/07/2023 (as and when required). | Assistant Engineer |  | ORD/000410/2023-2024 | 800/KSD | 16/06/2023 | 16/09/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 2161/ND | 18/05/2022 | 18/05/2022 | Resource Division | 214.18 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2021-2022 | 1396/ND | 24/03/2022 | 24/03/2022 | Resource Division | 33.5 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 4270/ND | 29/09/2022 | 29/09/2022 | Resource Division | 8.85 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BARA ANDULIA W/S Scheme, Block- Chapra , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 03) |  |  | ORD/000897/2022-2023 | 407/EMD | 20/01/2023 | 19/02/2023 | CONCORD ENGINEERING | 26.28 | 0 | 0 | 0
7 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 lVltrs' Depth) by utilizing Departmental Machineries for Bara Andulia w/s scheme (Z-t, T/w-l & ll) , Chapra Block under Nadia District, Central Drilling Division, p.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 1227/CDD | 04/09/2023 | 30/06/2024 | MENAKA ENTERPRISE | 37.76 | 15.23 | 40.34 | 50
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Quotation for new service connection charges and security deposit for PH-4 under Bara-Andulia(Zone-I) w/s scheme, Under EMSD-III,PHE Dte,Nadia |  |  | BILL/01811/2024-2025 | BP-157-24-25 | 06/11/2024 | 06/11/2024 | W.B.S.E.D.C.L (GROUP CHAPRA C.C.C) | 5.06 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction Of 750 Cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 750 Cum Ohr Of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Bara Andulia-I to accommodate FHTC within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3,Junior Engineer 4 | ORD/000016/2022-2023 | 2055/ND | 10/05/2022 | 01/01/2027 | TARUN KUMAR BHATTACHARYA | 640.03 | 313.16 | 48.93 | 48
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Bara Andulia Zone-I Water Supply Scheme within Chapra Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000788/2023-2024 | 1899/ND | 15/03/2024 | 10/03/2025 | HARBAUER INDIA (P) LTD. | 300.5 | 0 | 0 | 20
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Laying Of Additional Distribution System Including Specials to provide FHTC at Leftout Household in connection with JJM In Ground Based Piped Water Supply Scheme at Bara Andulia Zone I To Accommodate FHTC Within Chapra Block Under Krishnanagar Sub-division Under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000316/2025-2026 | 4504/ND | 18/09/2025 | 17/12/2025 | S.S.INFRASTRUCTURE | 68.11 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bara Andulia Zone I Water Supply Scheme within Chapra block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000488/2023-2024 | 6115/ND | 21/12/2023 | 19/04/2025 | SAHA ENGINEERS | 12.16 | 8.93 | 73.42 | 20
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte | SM/10037 | Augmentation | Construction of 2 nos Pump House, Land Development and Boundary Wall at 3rd T/W and 4th T/W site for Bara Andulia Zone I Water Supply Scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000280/2024-2025 | 6631/ND | 25/10/2024 | 17/05/2025 | M/S S.K. ENTERPRISE | 29.92 | 3.71 | 12.39 | 70
Total | [13 empty] | 1381.66 | 341.03 | 24.68