## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. |  |  | VCH/001073/2021-2022 | 636/PFMS | 16/03/2022 | 16/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.5 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Bhaluka Water Supply Scheme under Krishnagar Sub-Division under Nadia Division, PHE Dte. (Sm/10068) | Assistant Engineer | Junior Engineer 3 | ORD/000034/2023-2024 | 2102/ND | 15/05/2023 | 13/08/2023 | B.M. ENGINEERING & CONSTRUCTION | 29.75 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 2160/ND | 18/05/2022 | 18/05/2022 | Resource Division | 152.87 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2021-2022 | 1388/ND | 24/03/2022 | 24/03/2022 | Resource Division | 33.49 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 3306/ND | 27/07/2022 | 27/07/2022 | Resource Division | 36.72 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Bhaluka Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000474/2023-2024 | 152/ND | 09/01/2024 | 09/03/2024 | JOYGOPAL GUPTI | 18.06 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Costruction of R.C.C eleveted reservoir 750 CUM all complete & Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Bhaluka to accommodate FHTC within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000011/2022-2023 | 1887/ND | 25/04/2022 | 01/07/2025 | M/S S.S ENTERPRISE | 786.78 | 0 | 0 | 80
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BHALUKA W/S Scheme, Block-Krishnagar-1, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000896/2022-2023 | 406/EMD | 20/01/2023 | 27/07/2025 | M.S. ENTERPRISE | 29.23 | 0 | 0 | 50
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of capacity 137 m3/hr at Bhaluka Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000191/2024-2025 | 5046/ND | 13/09/2024 | 07/03/2026 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 318.54 | 0 | 0 | 70
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/10068 | Augmentation | Construction of Additional Boundary wall and allied works at Headwork Site at Bhaluka Water Supply Scheme within Krishnagar-I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000052/2025-2026 | 2289/ND | 19/05/2025 | 14/01/2026 | JOYGOPAL GUPTI | 29.78 | 0 | 0 | 50
Total | [13 empty] | 1439.73 | 0 | 0