## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS |  |  | VCH/001136/2021-2022 | 702/PFMS | 30/03/2022 | 30/03/2022 | HORIZEN | 2.8 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC at under SHYAMNAGAR W/S Scheme, Block-Tehatta I , Dist. - Nadia. NIET No. 36 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 1584/EMD | 24/04/2023 | 24/05/2023 | P.K. ENTERPRISE | 16.13 | 0 | 0 | 80
3 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Augmentation of Distribution System of Ground Based Piped Water Supply Scheme at Shyamnagar to accommodate FHTC within Tehatta I Block under Kalyani Sub Division I under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000306/2023-2024 | 4276/ND | 21/09/2023 | 20/11/2023 | MONDAL ENTERPRISE | 20.56 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2021-2022 | 1389/ND | 24/03/2022 | 24/03/2022 | Resource Division | 29.18 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2022-2023 | 151/ND | 06/01/2023 | 06/01/2023 | Resource Division | 1.84 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 2318/ND | 29/05/2023 | 29/05/2023 | Resource Division | 24.17 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Laying distribution system for providing FHTC at Chilakhali Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000765/2023-2024 | 1818/ND | 14/03/2024 | 12/06/2024 | M/S.ROY CHOWDHURY & CO | 54.33 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at Head Work site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000667/2023-2024 | 1099/ND | 19/02/2024 | 19/04/2024 | K.K. MARKETING | 9.87 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Repair & Renovation of Pump House and Construction of Boundary wall, Service Road and allied works at 2nd T.W site under Shyamnagar PWSS under Tehatta-I Block in Nadia District Under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000762/2023-2024 | 1725/ND | 12/03/2024 | 11/05/2024 | BABLU MALLICK | 10.44 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Construction of Jhama Bats Road from Palassey Betai road to headwork site of Shyamnagar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000816/2023-2024 | 481KLYSD-I | 15/03/2024 | 14/04/2024 | MONDAL ENTERPRISE | 6.03 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 500 cum Capacity 20 Mtr. Staging Height Rcc Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost of Pipes, Specials and Soil Investigation for Augmentation of Ground Based Water Supply Scheme at Shyamnagar to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000429/2022-2023 | 844/ND | 28/02/2023 | 28/02/2026 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 580.91 | 0 | 0 | 58
12 | NADIA |  | Nadia Division | Providing FHTC by augmentation under Jal Swapna for Shyamnagar PWSS | SM/10074 | Augmentation | Construction and Installation of 120.00 cum capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Shyamnagar PWSS including 3 Months Trial Run & 3 Years O&M under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000743/2023-2024 | 1588/ND | 06/03/2024 | 02/09/2024 | MONDAL ENTERPRISE | 300.5 | 0 | 0 | 50
Total | [13 empty] | 1056.76 | 0 | 0